## PROJECT INFO
National Church Residences
HOOVER PLACE APARTMENTS |  | DATE PUBLISHED | 43850
5407 Hoover Avenue, Dayton, Ohio 45417 |  | DATE PRINTED | 2020-08-28
REHABILITATION WORK SCOPE ‐ DRAFT
PROJECT SUMMARY
Hoover Place Apartments, originally construction in 1998, in an existing 144 unit 3-story Affordable Living Senior Independent-Living apartment building located in Dayton, Ohio. The building, constructed slab-on-grade with wood framing above, cladding consists of brick and vinyl siding. It has been noted by building maintenance staff (unverified at this time by Architect's office), that the exterior sheathing in not protected with an exterior building wrap - design documents identify an exterior insulation board that may substitute the need for an exterior building wrap. Additionally, it has been noted by building staff and design documents (provided by National Church Residences) that the building does not contain ANSI Type 'A' units and units will be modified to meet Fair Housing Act Guidelines on an 'as-needed' basis. The proposed renovation of Hoover Place includes limited site, exterior and interior common area and dwelling unit improvements. The proposed renovation will be completed in phases. The proposed site, exterior facade and the common area renovation work (greatest extents possible) to be completed concurrently.
EXISTING DEVELOPMENT
• 3-story, senior independent living apartment buildings (158,678 gross s.f.) set on approximately 5.624 acres. • One hundred forty-four (144) total dwelling units. Eight (8) one-bedroom units. One hundred thirty-six (136) two-bedroom units. Eight (8) are ANSI/ICC handicap compliant dwelling units are included. • Existing resident parking capacity is (112) total spaces which include (5) spaces designated for handicap accessibility and. One (1) van accessible space is included in the quantity of handicap accessible parking spaces. • The building is slab on grade construction with wood framed exterior walls with brick veneer; wood framed interior walls and wood framed roof.
WORK SCOPE SUMMARY
Unless otherwise indicated due to structural impracticality of existing conditions, all new construction shall be congruent with current Accessibility Standards and OHFA Universal Design Features to the greatest extent possible. Appliances, mechanical systems and lighting to be Energy Star rated - Enterprise Green Communities Requirement. All paints, primers, adhesives, sealants, composite wood products and flooring are to meet Enterprise Green Communities Requirements. Reference the Property Condition Needs Assessment and Phase I Environmental Site Assessment Report for more detailed information. R/R = Remove and Replace Sustainable Design Requirements This Project will be developed to meet Enterprise Green Communities and will meet all prerequisite requirements as well as select elective credits.
KEY:
Priority (P)
Maybe (M)
No (N)

## SCOPE
| PROGRAM |  |  |  | PRICING
| CODE | ROOM | Origin of Scope | Remarks | Trade Item | Quantity: Area | Quantity: Count | Price Per Unit | Budget Expectations - Auto | Budget Goal - Manual | VE (MM/DD/YYYY) | VE (MM/DD/YYYY) | VE (MM/DD/YYYY)
| EV | ENVIRONMENTAL
| 1 | Passive radon mitigation systems. | Funding Agent Requirement | TBD | 02 - Earth Work |  |  | 0 | 0 | 0
| 2 | Phase I has not been completed at this time. | Phase 1 | TBD |  |  |  | 0 | 0 | 0
SITE
PARKING
p | 1 | Reconfigure handicap parking and stripping. Remove and replace 5 handicap parking signs. 4 handicap signs and 1 van accessible sign. | PCNA 2017, Accessibility | PCNA reported cross-slopes in non-compliance | 02 - Roads and Walks |  |  | 0 | 0
EARTHWORK
m | 2 | Add soil and re-grade away from building foundation minimum 5% for a distance of 10'-0" as required. Re-seed. | PCNA 2017, Accessibility | Erosion at south side of building | 02 - Earth Work |  |  | 0 | 0
p | 3 | Grades and means of egress to public way. Correct site access and accessibility. Provide an allowance | PCNA 2017, Accessibility |  | 02 - Earth Work |  |  | 0 | 0
m | 4 | Provide 18” wide perimeter gravel on fabric at base of building. | Architects Recommendation |  | 02 - Earth Work |  |  | 0 | 0
CONCRETE & FLATWORK
| 5 | Configure sidewalk connecting points to egress discharge at ROW | PCNA 2017, Accessibility | PCNA reported that north side parking area sidewalks appear to meet the requirements for ramps, but exist without the required components for ramps. Options to rebuild sidewalks to be compliant with slopes or convert sidewalks to ramps. | 02 - Roads and Walks |  |  | 0 | 0
| 6 | Remove and replace existing concrete building entry slab; new slab to meet accessibility requirements for slopes. | PCNA 2017, Accessibility |  | 02 - Roads and Walks |  |  | 0 | 0
| 7 | Remove and replace concrete walk along front of building at handicap parking. Provide flush curb at pavement with tactile warning. | PCNA 2017, Accessibility |  | 02 - Roads and Walks |  |  | 0 | 0
p | 8 | Grind trippers at portions of existing concrete sidewalks to accommodate slope requirements. A tripper is defined as a variance in height of more than 1/2" between adjoining slabs - 60 LF allowance. | PCNA 2017, Accessibility |  | 02 - Roads and Walks |  |  | 0 | 0
m | 9 | Remove and replace areas of cracked or uneven stretches of concrete walk - 200 SF allowance. | Architects Recommendation |  | 02 - Roads and Walks |  |  | 0 | 0
m | 10 | Remove and replace portions of damaged existing concrete curbs. | Architects Recommendation |  | 02 - Roads and Walks |  |  | 0 | 0
FENCING
m | 11 | Remove and replace aluminum fence. Provide new 6'-0" height aluminum fence around perimeter of site. | Architects Recommendation |  | 02 - Site Improvements |  |  | 0 | 0
LANDSCAPING
p | 12 | Landscape allowance ($20,000) | Architects Recommendation |  | 02 - Lawns and Plantings |  |  | 0 | 0
p | S3 | Remove and replace dead or dying vegetation - landscaping shall be native and non-invasive species. | OHFA Design Standard |  | 02 - Lawns and Plantings
m | S4 | Construct new pavilion (Covered Patio) | Design Element |  | 06 - Rough Carpentry
m | S5 | Remove and replace flag pole: provide new 30' pole with internal halyard; provide new ground mounted up-lighting. Provide two (2) new (site) post mounted lights and posts. | Useful Life Duration Limit |  | 10 - Specialities
m | S6 | Remove and replace site post mounted lighting and post; concrete base to remain, clean and seal. Provide two (2) new (site) post mounted lights and posts. | Architects Recommendation |  | 16 - Electrical
p | 17 | Remove and replace new wood trash enclosure fencing with new split face block refuse enclosure. | Useful Life Duration Limit |  | 01 - General Requirements |  |  | 0 | 0
UTILITIES
m | 18 | Inspect and clear all underground roof drainage conduit. Clear any sections by jet spray method. | Architects Recommendation |  | 07 - Roofing |  |  | 0 | 0
m | S9 | Inspect all existing sanitary lines from building to street. Remove, repair, replace or clean as required. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
m | S10 | Inspect and clean existing parking area catch basins. | Architects Recommendation |  | 02 - Earth Work |  |  | 0 | 0
m | S11 | Inspect and clean all existing yard catch basins/drains. Re-grade away from inlet as required and re-seed. | Architects Recommendation |  | 02 - Earth Work |  |  | 0 | 0
p | S12 | Extend existing downspouts downspout extension on gravel with splash block and fabric per detail. | Architects Recommendation |  | 07 - Sheet Metal |  |  | 0 | 0
p | 23 | Provide new exterior security cameras mounted to the two (2) new post mounted lights. | Architects Recommendation |  | 16 - Electrical |  |  | 0 | 0
OTHER
p | 24 | Remove and replace with owner approved monument signage | NCR Design Standard | There are two (2) existing monument signs. Discuss to determine the quantity to be replaced. | 10 - Specialities |  |  | 0 | 0
m | 25 | Remove and replace existing benches | Architects Recommendation |  | 02 - Site Improvements |  |  | 0 | 0
m | 26 | Remove and replace metal loading dock railing - paint safety yellow. Include removable section for deliveries. | Architects Recommendation |  | 02 - Site Improvements |  |  | 0 | 0
| BE | BUILDING EXTERIOR
p | 1 | Remove and replace 15% vinyl siding and trim from entire building down to exterior wall sheathing or masonry base in preparation for new exterior wall treatments indicated on proposed elevations. Install new cladding as follows - a. Provide allowance for 25% replacement of existing exterior grade sheathing (unknown).; a.(i) Note: Provide alternate pricing to install commercial grade exterior weather barrier material. Destructive demolition to occur at a later date to identify the wall construction/assembly. b. Provide allowance for 25% replacement of exterior insulation board. b(i). Note: This condition has not been verified at this time. Destructive demolition to occur at a later date to identify the wall construction/assembly. c. Provide allowance for 25% replacement of existing wood framing with staggered 2x framing. d. Provide allowance for 25% replacement of existing batt wall insulation. e. Install fiber-cement lap siding fastened to substrate/furring strips. e(i) Add/alternate based on existing wall construction assembly: Install new 2" type II EPS rigid insulation adhered to sheathing with adhesive and mechanically fastened to existing 24" o.c. metal stud furring. e(ii). Add/alternate: Install 1x4 wood furring with 3/4" rigid foam insulation. e(iii). Add/alternate: Infill furring spacings with 3/4" rigid foam insulation. e(iv). Add/alternate: Install house wrap drainage plane. Exterior trim: All windows and doors and inside/outside corners are to receive 4" (w) 5/4 inch fiber cement trim. | Architects Recommendation | Owner to confirm scope | 07 - Insulation |  |  | 0 | 0
p | 2 | Power wash 100% of vinyl siding; clean exterior. | PCNA 2017, Accessibility | Algae and residue build-up noted by PCNA to require cleaning | 07 - Waterproofing |  |  | 0 | 0
p | 3 | Remove and replace all sealants and caulking. | Due Diligence |  | 07 - Waterproofing |  |  | 0 | 0
p | 4 | Repair select areas of brick rowlock sill at top course and corners of foundation. | PCNA 2017, Accessibility | Observed damage reported at the west elevation of the southeast wing. Repair door and frame. | 04 - Masonry |  |  | 0 | 0
n | 5 | Existing brick veneer to remain. | Architects Recommendation |  | 04 - Masonry |  |  | 0 | 0
n | 6 | Existing brick soldier course to remain. | Architects Recommendation |  | 04 - Masonry |  |  | 0 | 0
n | 7 | Existing brick window sill to remain. | Architects Recommendation |  | 04 - Masonry |  |  | 0 | 0
p | 8 | Replace automatic bi-parting storefront entrance doors. | Useful Life Duration Limit |  | 08 - Doors |  |  | 0 | 0
p | 9 | Existing sliding doors to remain. Provide ADA compliant interior and exterior ramps as required. | Code Requirement |  | 02 - Roads and Walks |  |  | 0 | 0
| BE | WINDOWS
p | 10 | Remove and Replace Windows with vinyl windows with low-e dual pane glazing comparable or equal to Quaker Manchester Series.100% of vinyl siding; clean exterior. | Useful Life Duration Limit |  | 08 - Windows |  |  | 0 | 0
p | 11 | Remove and replace plastic laminate window sill with new cultured marble. | Architects Recommendation |  | 08 - Windows |  |  | 0 | 0
p | 12 | Remove and replace wall vents/louvers and seal/caulk as required. | Due Diligence |  | 07 - Waterproofing |  |  | 0 | 0
| BE | UNIT BALCONIES
p | 13 | Remove and replace dwelling unit exterior sliding patio doors, door frame and door threshold, prep opening to receive new door. | PCNA 2017, Accessibility | Change in level between interior of dwelling unit and balcony at sliding door thresholds reported to be 1.5". Balconies to be rebuilt to change this or ramp to be added. Location reported at 2nd floor and 3rd floor dwelling units. | 08 - Doors |  |  | 0 | 0
p | 14 | Dwelling Unit Balconies: Remove top rail. Secure balusters to be reused with new top rail (Rebuild per 2/A602). Rebuild balconies with new balcony decks, and raise balcony level for accessible travel through balcony door. Remove and replace all wood decks inclusive of all decking and structural framing (ledgers, beams, columns, etc.): to be demolished including existing foundations down to 24" below grade; structural shoring for roof elements supported by existing 6x6 pressure treated posts. | Architects Recommendation | Owner to confirm scope. | 06 - Rough Carpentry |  |  | 0 | 0
| BE | SKYLIGHTS
p | 15 | Remove and replace existing skylights, sealants and caulking. Verify condition of existing flashing/weatherproofing and replace as required. | Useful Life Duration Limit | Assumed that these windows were installed and match the building windows life span. | 08 - Windows |  |  | 0 | 0
| BE | ROOF
p | 16 | Remove and replace existing asphalt shingles with new. Replace all existing drip edge, valley flashing, step and counter flashing, parapet coping, roof penetration flashings and vents. New shingles shall be 30-year dimensional shingles with ice guard at eaves and valleys. Provide allowance for 20% sheathing replacement. | Useful Life Duration Limit |  | 07 - Roofing |  |  | 0 | 0
p | 17 | Provide new valley flashing, see detail C/A104 - Valley flashing in accordance with SMACNA Figure 4-10. | Architects Recommendation |  | 07 - Roofing |  |  | 0 | 0
p | 18 | Existing roof to remain. New roof penetrations to be flashed and sealed. | Architects Recommendation | Owner to confirm scope. | 07 - Roofing |  |  | 0 | 0
p | 19 | Remove and replace aluminum fascia; Remove and replace pre-finished aluminum downspout, splash blocks and downspout boots. Downspout drainage leaders are to be scoped and jet cleaned to daylight or to storm drainage system. | Useful Life Duration Limit |  | 07 - Sheet Metal |  |  | 0 | 0
| EL | ELECTRIC / LIGHTING
p | 1 | Remove and replace all wall mounted decorative lighting with upgraded Energy Star lighting package on photocell. | OHFA Design Standard |  | 16 - Electrical |  |  | 0 | 0
m | 2 | Remove and replace all wall mounted security lighting. Provide new exterior security cameras mounted to the two (2) new post mounted lights. | Architects Recommendation | Owner to confirm scope. | 16 - Electrical |  |  | 0
BUILDING INTERIOR (NON-UNIT / DWELLINGS)
| AT | ATTIC
m | 1 | Provide blown-in attic insulation to increase overall R-value to R49. | Code Requirement |  | 07 - Insulation |  |  | 0 | 0
m | 2 | Attic bypass air sealing in properties when insulation is required to be added. Bypass is defined as any building air leakage pathway between conditioned and unconditioned areas. Attic bypass locations included but are not limited to chimney chases, combustion/soil stack chases, open wall tops, dropped ceilings, open plumbing walls, beneath knee walls, around ductwork, electrical work and attic access points. Attic bypasses are sealed in such a manner that the movement of air is "Essentially Stopped". "Essentially Stopped" means that air leakage will not be detected by an infrared scan when the house of dwelling unit is depressurized at 25 Pascals. Materials used for bypass sealing are determined by the size and location of the bypass. These materials include high quality caulking with 20-year life span, polyethylene rod stock, spray foam, gypsum board, sheet metal, extruded polystyrene insulation and densely packed insulation. | OHFA Design Standard |  | TI: Pick from Menu |  |  | 0 | 0
| SW | EGRESS STAIRWELLS
p | 1 | Install new exterior thermal glazed insulated door | Useful Life Duration Limit |  | 08 - Doors |  |  | 0 | 0
p | 2 | Remove and replace all flooring and base. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0
m | 6 | Paint entire stairwell: Prep walls to receive new paint - Assume 25 SF of patch and repair of existing wall condition. Walls to be prepped to like new defect free condition. Low/No VOC paints and primers. | OHFA Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0
m | 7 | Existing stairwell handrails are to be inspected for structural stability. Railings shall meet 250 LB/FT of resistance as required by code. Re-secure with new through-bolts. | Code Requirement |  | 10 - Specialities |  |  | 0 | 0
p | 8 | Remove and replace 1-hour rated metal door. Remove and replace all existing door hardware with code compliant lever and panic hardware. Provide seals and gaskets. All stair doors are to be prepared to receive new paint - preparation to include all required patching and repairing (filling of any holes with UL approved patch) and prime coat to place door in "like-new" condition. Low/No VOC paints and primers. | Code Requirement |  | 08 - Doors |  |  | 0 | 0
| CAD | COMMON AREA DEMOLITION (GENERAL ALL FLOORS)
p | 1 | Remove storefront system completely at designated first floor exterior entrances and vestibules. | Useful Life Duration Limit |  | 08 - Glass |  |  | 0 | 0
p | 2 | Remove door, door casing, door frame, and hardware completely. 1st Floor Rooms: Stair SE-1, Electrical Room, Stair SW-1, Stair NW-1, Stair NC-1, Stair NE-1, Staff Lounge Closet, Rear Patio Vestibule & Sidelight. | Architects Recommendation |  | 08 - Doors |  |  | 0
p | 3 | Remove all finish flooring on all levels down to concrete slab on grade or gypcrete, prep floor to receive new flooring finish - see finish schedule. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  | 0
p | 4 | Remove wall base completely. Typical all common areas. | OHFA Design Standard |  | 06 - Finish Carpentry |  |  | 0
m | 5 | Remove wainscot (where present) and chair rail completely in common areas. | Architects Recommendation |  | 06 - Finish Carpentry |  |  | 0 | 0
p | 6 | Remove mail station completely. | Code Requirement |  | 10 - Specialities |  |  | 0 | 0
p | 7 | Remove reception desk completely. | Design Element | Additional investigation is required to determine if any code requirements are also a contributer to replacement. | 06 - Finish Carpentry |  |  | 0 | 0
m | 8 | Remove decorative column casing, encased structural column to remain, protect throughout the duration of construction. Low/No Formaldehyde emitting wood products. | Architects Recommendation |  | 09 - Drywall |  |  | 0 | 0
p | 9 | Remove and replace portion of concrete slab on grade as required for radon pit construction and routing of soil gas piping, dowel into existing slab and replace vapor barrier and concrete slab on grade to be flush with existing concrete slab. This scope only to be completed in units requiring radon pipes. | Architects Recommendation |  | 03 - Concrete |  |  | 0 | 0
p | 10 | Remove and Replace surface mounted fire extinguisher and hanging hardware | Code Requirement |  | 10 - Specialities |  |  |  | 0
p | 11 | Remove all heat pump units and air handlers completely - see mechanical drawings. Replacement heat pump shall be Energy Star Qualified | Useful Life Duration Limit |  | 15 - Heat and Ventilation |  |  | 0
p | 12 | Remove cabinets, countertop and backsplash and associated plumbing fixtures, remove supply and waste lines back to source and cap below floor structure - see plumbing drawings. Low/No Formaldehyde emitting wood products. | Useful Life Duration Limit |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 13 | Remove shelving and associated hardware completely. | NCR Design Standard |  | 11 - Cabinets |  |  | 0 | 0
m | 14 | Remove popcorn ceiling finish at ceilings and underside of stairwell, stair stringers, typical all common areas. Provide cost as deduct alternate. | Architects Recommendation |  | 09 - Drywall |  |  | 0 | 0
p | 15 | Remove plastic laminate window stools completely. | Architects Recommendation |  | 08 - Windows |  |  | 0
m | 16 | Remove existing load bearing wall and/or segment (F.V. extent of demolition), G.C. to provide temporary shoring as required - see proposed architectural and structural plans for extent of demolition. ** G.C. to coordinate all rough opening dimensions prior to demolition. Location: 1st Floor at Beauty Shop & Directors Office. | Design Element |  | 09 - Drywall |  |  | 0 | 0
m | 17 | Inspect existing handrails for structural stability. Railings shall beet a uniform load resistance of 50 lbs/ft or a concentrated load of 200 lbs placed at the top of the handrail or guard. | Code Requirement |  | 10 - Specialities |  |  | 0 | 0
p | 18 | Remove all stairway flooring and base at landings. Remove existing base trim. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  | 0
p | 19 | Remove unit entry door, door casing, door frames and door hardware completely. | Useful Life Duration Limit |  | 08 - Doors |  |  | 0
p | 20 | Remove interior glazing completely. Location TBD. | Design Element | Owner to confirm scope. | 08 - Windows |  |  | 0
p | 21 | Remove HVAC unit - See mechanical drawings for extent of demolition. Heat pumps shall be Energy Star Qualified. Cooling equipment ≥ 13 SEER | PCNA 2017, Accessibility |  | 15 - Heat and Ventilation |  |  | 0
p | 22 | Remove window completely for replacement. Location TBD | Design Element | Owner to confirm scope. | 08 - Windows |  |  | 0
p | 23 | Remove condensing units and line sets completely - See mechanical drawings Cooling equipment ≥ 13 SEER | PCNA 2017, Accessibility |  | 15 - Air Conditioning |  |  | 0
p | 24 | Remove unit heater, typical all stairwells - See mechanical drawings. | PCNA 2017, Accessibility |  | 15 - Heat and Ventilation |  |  | 0
p | 25 | Remove all interior signage completely. | NCR Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0
p | 26 | Remove and replace 10% aluminum fascia; and all gutters and downspouts. Pre-finished aluminum downspout, remove and replace existing downspouts, splash blocks and downspout boots. Downspout drainage leaders are to be scoped and jet cleaned to daylight or to storm drainage system. | Useful Life Duration Limit |  | 07 - Roofing |  |  | 0
p | 27 | Prep walls to receive new paint: assume 25 SF of patch and repair of existing wall condition. Walls to be prepped to like new defect free condition. | PCNA 2017, Accessibility |  | 09 - Painting and Decorating |  |  |  | 0
p | 28 | Remove balcony and posts entirely. | Due Diligence |  | 06 - Rough Carpentry |  |  | 0
p | 29 | Remove sliding glass door. Prep rough opening for new glazed system. | Architects Recommendation |  | 08 - Doors |  |  | 0
p | 30 | Remove skylight. Prep rough opening for new glazing system. | Useful Life Duration Limit |  | 08 - Windows |  |  | 0
p | 31 | Shore existing roof for post and balcony removal. | Due Diligence |  | 06 - Rough Carpentry |  |  | 0
p | 32 | Remove existing main entry and rear patio doors and sidelights. | Architects Recommendation |  | 08 - Doors |  |  | 0
p | 33 | Remove all existing interior area metal flat panel doors and metal frames common to lobbies, gathering spaces and corridors. | Architects Recommendation |  | 08 - Doors |  |  | 0 | 0
m | 34 | Remove all ceiling tile, grid and supports. | Architects Recommendation |  | 09 - Acoustical |  |  | 0 | 0
p | 35 | Remove all existing lighting, to be replaced with upgraded Energy Star lighting package. | Architects Recommendation |  | 16 - Electrical |  |  | 0 | 0
p | 36 | Remove ceiling fans. | Architects Recommendation |  | 16 - Electrical |  |  | 0 | 0
p | 37 | Remove laundry sink. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 38 | Remove kitchen cabinets. | Architects Recommendation |  | 11 - Cabinets |  |  | 0
| CA | COMMON AREA (GENERAL ALL FLOORS)
p | 1 | Correct interior accessibility issues | Code Requirement |  | 01 - General Requirements |  |  | 0
| CA | COMMON AREA FLOORING (GENERAL ALL FLOORS / UNLESS NOTED OTHERWISE)
p | 2 | New flooring in all areas (Vinyl flooring and tile at common areas, carpet in offices, vinyl flooring in entire unit except bedroom and bedroom closet, bedroom and bedroom closet to receive carpet.) Remove existing flooring finish down to concrete slab on grade and gypcrete, prep floor to receive new flooring finish - see finish schedule. Remove and replace all flooring on all levels. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0
p | 3 | Corridors: Correct interior gypcrete failures. Repairs on 2nd and 3rd floors. Repair areas with 1/4" or greater Tripping hazard. Provide 3500 PSI minimum strength.nd replace existing vinyl base with new painted 1x4 with roman ogee edge. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0
m | 4 | Corridors: Remove and replace existing vinyl base with new painted 1x4 with roman ogee edge. Low/No VOC adhesives and sealants. | Architects Recommendation |  | 09 - Resilient Flooring |  |  | 0 | 0
| CA | COMMON AREA PAINT (GENERAL ALL FLOORS / UNLESS NOTED OTHERWISE)
p | 5 | Paint - All common spaces to be painted including drywall repair. Repaint 100% of all common areas, administrative areas. Low/No VOC paints and primers. | OHFA Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0
p | 6 | New 2-tone paint; one color above handrail/chair rail and contrasting color below. Add painted wood chair rail to common areas. Prime and paint all existing, exposed CMU walls. Low/No VOC paints and primers. | OHFA Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0
p | 7 | Provide new wood handrail with new 3-1/2" trim banding. Install 5-1/2" chair rail opposite wall in corridors. Low/No VOC paints and primers. Low/No Formaldehyde emitting wood products. | OHFA Design Standard | In Lineal Foot | 09 - Painting and Decorating |  |  | 0 | 0
| CA | COMMON AREA DOORS & HARDWARE (GENERAL ALL FLOORS / UNLESS NOTED OTHERWISE)
p | 8 | Remove and replace all door hardware throughout building with new hardware package. | Useful Life Duration Limit |  | 08 - Doors |  |  | 0 | 0
p | 9 | Remove and replace entrance vestibule storefront | Useful Life Duration Limit |  | 08 - Doors
p | 10 | Replace existing main entry and rear patio doors and sidelights. Install new by-parting aluminum door systems at front entry. Provide cost as deduct alternate. | Useful Life Duration Limit |  | 08 - Doors
p | 11 | Install new Redi Frame interior metal door frames at new openings. Install wood door casings. | Architects Recommendation |  | 08 - Doors |  |  | 0 | 0
p | 12 | Install "prop-open" alarms at exterior exit doors and rear 1st floor vestibule doors. | Architects Recommendation | Owner to confirm scope. | 08 - Doors |  |  | 0 | 0
p | 13 | Remove and replace 20% of interior doors and hardware. Doors to match existing. | Architects Recommendation | Owner to confirm scope. | 08 - Doors |  |  | 0 | 0
p | 14 | All existing interior doors are to be prepped to receive new paint - prep to include all required patching and repairing (filling of any holes with UL approved patch) and prime coat to place door in "like-new" condition. | Architects Recommendation |  | 08 - Doors |  |  | 0 | 0
| 15 | Based on Schlage ‘AL’ series with Neptune lever handle design. Unless noted otherwise - All new door hardware locks and sets at existing and newly installed doors. | Architects Recommendation |  | 08 - Doors |  |  | 0 | 0
p | 16 | At public restrooms, new door hardware shall indicate "occupied" or "vacant". | Code Requirement |  | 08 - Doors |  |  | 0 | 0
| CA | COMMON AREA MAIL STATION
p | 17 | 150 +/- ADA/ANSI, USPS compliant mail station adjacent entry lobby. Cluster box units, and front loading mailbox suites. Demolish existing mail room and mail station. Enlarge lobby. | Code Requirement |  | 11 - Special Equipment
| CA | COMMON AREA CEILINGS (GENERAL ALL FLOORS / UNLESS NOTED OTHERWISE)
m | 18 | Replace ceiling tile. Replace all acoustic ceiling panels and grid. Install new 2x2 tegular edge panels in 1st floor lobby space and offices. | Architects Recommendation | Owner to confirm scope. | 09 - Acoustical |  |  | 0 | 0
p | 19 | Repair moisture damage and other select areas of discolored ceilings and/or damage. Refurbish to level four finish. Low/No VOC paints and primers. | PCNA 2017, Accessibility | Repair noted to be in activities room from 2nd floor leak. Remediate any mold. | 09 - Drywall |  |  | 0 | 0
| CA | COMMON AREA FINISHES, ACCESSORIES & INSTALLATIONS (GENERAL ALL FLOORS / UNLESS NOTED OTHERWISE)
m | 20 | Convert existing Beauty Salon to visiting doctor's examination room with waiting area. Low/No VOC paints and primers. Low/No VOC adhesives and sealants. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0
p | 21 | Replace all finishes in Managers Office. Low/No VOC paints and primers. Low/No VOC adhesives and sealants. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 09 - Painting and Decorating
p | 22 | Mini-Blinds: install at all exterior windows. | Design Element | Owner to confirm scope. | 12 - Blinds and Shades, Artwork |  |  | 0 | 0
m | 23 | Remove existing non-load bearing walls and/or segment (F.V. extent of demolition) - See proposed architectural plans for extent. Location: At existing Director's Office and existing Beauty Shop. | Architects Recommendation | Adjustment of program. | 09 - Drywall |  |  | 0 | 0
m | 24 | Remove and replace all existing wood handrail with new wood handrail with chair rail opposite wall in corridors. Extend handrail throughout common area lobbies. Low/No Formaldehyde emitting wood products. Provide new wood handrail with new 3-1/2" trim banding. Install 5-1/2" chair rail opposite wall in corridors. Low/No VOC paints and primers. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 06 - Finish Carpentry |  |  | 0 | 0
p | 25 | Replace all interior signage with new NCR standard signage. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 10 - Specialities
p | 26 | See common area finishes | NCR Design Standard |  | 09 - Painting and Decorating
p | 27 | Remove and replace all 3rd floor 1-hr rated metal access panel assemblies with new code compliant panels. | Architects Recommendation |  | 10 - Specialities |  |  | 0 | 0
p | 28 | New computer room casework elevations. Low/No VOC adhesives and sealants. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 06 - Finish Carpentry |  |  | 0 | 0
p | 29 | Provide new wood 6” base at public common areas. | Architects Recommendation |  | 06 - Finish Carpentry
| LR | LAUNDRY ROOMS (ALL FLOORS)
p | 1 | Replace VCT and base trim. Low/No VOC adhesives and sealants. | OHFA Design Standard | Included in Common Area Cost Above | 09 - Resilient Flooring |  |  | 0 | 0
m | 2 | Replace acoustic ceiling tile and grid | Architects Recommendation |  | 09 - Acoustical |  |  | 0 | 0
p | 3 | Install new plastic laminate folding counter. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 11 - Cabinets |  |  | 0 | 0
m | 4 | Replace existing equipment. One set shall be an accessible washer and dryer. (Laundry equipment N.I.C. - by Owner.) Dryers are to be vented to the exterior with rigid ducting. | OHFA Design Standard | PCNA Immediate Repair for cleaning dryer ducting and dryer vents. | 16 - Electrical |  |  | 0 | 0
m | 5 | Provide electric for new vending machine area. | Architects Recommendation |  | 16 - Electrical |  |  | 0 | 0
| CR | COMMUNITY ROOM
p | CR1 | Remove and replace existing rear patio vestibule doors and sidelights. Install new by-parting aluminum door systems at front entry. Provide cost as deduct alternate. | Useful Life Duration Limit |  | 08 - Doors |  |  | 0 | 0
p | CR2 | Replace lighting with new lighting package that is Energy Star compliant. | OHFA Design Standard | Included in Common Area Cost Above | 16 - Electrical |  |  | 0 | 0
m | CR3 | Replace ceiling fans. | Architects Recommendation |  | 16 - Electrical |  |  | 0 | 0
p | CR4 | Paint window and door casings. Low/No VOC paints and primers. | OHFA Design Standard | Included in Common Area Cost Above | 09 - Painting and Decorating |  |  | 0 | 0
p | CR5 | Replace existing resilient flooring - install new vinyl plank flooring and wood base. Low/No VOC adhesives and sealants. | OHFA Design Standard | Included in Common Area Cost Above | 09 - Resilient Flooring |  |  | 0 | 0
| CK | COMMUNITY KITCHEN
p | 1 | Remove and replace kitchen cabinets. Install new kitchen cabinets with wire pulls. Base cabinets to be 32" HC accessible with roll out shelving. Low/No VOC adhesives and sealants. Low/No Formaldehyde emitting wood products. | PCNA 2017, Accessibility | Location identified by PCNA to be at the Community Kitchen with the stove. | 11 - Cabinets |  |  | 0 | 0
p | 2 | Install plastic laminate countertops with molded backsplash. Low/No VOC adhesives and sealants. Low/No Formaldehyde emitting wood products. | OHFA Design Standard | Included in Number Above | 06 - Finish Carpentry |  |  | 0 | 0
p | 3 | Remove existing VCT flooring. Install new vinyl plank flooring extended under all removable equipment and open counter. Low/No VOC adhesives and sealants. | OHFA Design Standard | Included in Common Area Cost Above | 09 - Resilient Flooring |  |  | 0 | 0
p | 4 | Install 33" ADA compliant double bowl sink with lever faucet; Insulate plumbing. Provide valance and clear open space below. Kitchen faucets ≤ 2.0 gpf | PCNA 2017, Accessibility | PCNA reported that existing sink did not have accessible "hardware". Other locations included doctor's office sink, common restrooms and activities room. Provide lever operated fixtures. | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 5 | Remove and replace existing refrigerator. Install GE Energy Star 25.0 CU FT clean steel side-by-side refrigerator with dispenser; Model# GSL25JFTBS with in freezer icemaker. | PCNA 2017, Accessibility | Previous scope did not identify NCR standard Whirlpool refrigerators. Provide NCR standard appliance manufacturers. | 11 - Appliances |  |  | 0 | 0
p | 6 | Install In-Sink-Erator Badger 5 disposal | Useful Life Duration Limit |  | 11 - Appliances |  |  | 0 | 0
p | 7 | Remove existing range and hood. Install new microwave/over combo at accessible height. Microwave to have integrate recirculating hood fan. | PCNA 2017, Accessibility | PCNA Accessibility Repair noted that the existing range did not have front controls. | 11 - Appliances |  |  | 0 | 0
m | 8 | Install under cabinet mount task lighting. | Architects Recommendation |  | 11 - Cabinets |  |  | 0 | 0
p | 9 | Install 4" vinyl cove base. Low/No VOC adhesives and sealants. | OHFA Design Standard | Included in Common Area Cost Above | 09 - Painting and Decorating |  |  | 0 | 0
m | 10 | Remove and replace pantry shelving with wire shelving. | Architects Recommendation |  | 11 - Cabinets |  |  | 0 | 0
p | 11 | Replace window sills with cultured marble. Low/No VOC adhesives and sealants. | PCNA 2017, Accessibility | Included in Windows Above | 08 - Windows |  |  | 0 | 0
p | 12 | Paint window and door casings. | Architects Recommendation | Included in Common Area Cost Above | 09 - Painting and Decorating |  |  | 0 | 0
p | 13 | Remove and replace electric water cooler(s) with new relocated Hi-Low. | Code Requirement | Does this need to be Energy Star labeled/rated? | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 14 | Countertop extension at base cabinet with knee wall | Architects Recommendation |  | 11 - Cabinets |  |  | 0 | 0
m | 15 | Countertop detail with plastic laminate l-shaped brackets | Architects Recommendation |  | 11 - Cabinets |  |  | 0 | 0
| 16 | Removable sink base front detail and plumbing shield detail according to interior details on drawings. | Code Requirement |  | 11 - Cabinets |  |  | 0 | 0
| RR | RESTROOMS (MEN'S/WOMEN'S)
p | 1 | Enlarge entries for accessibility. 36" door panels are required. | Code Requirement |  | 06 - Rough Carpentry |  |  | 0 | 0
p | 2 | R/R existing plumbing fixtures with new Water Sense labeled fixtures | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 3 | Install accessible height surface mounted paper roll holder, surface mounted paper towel dispenser with integral waste receptacle, Wall mounted soap dispenser and robe hook. | Code Requirement |  | 11 - Special Equipment |  |  | 0 | 0
| 4 | Install plate glass mirror full width of vanity. | NCR Design Standard | Included in Cost Above | 11 - Special Equipment |  |  | 0 | 0
p | 5 | Install non-slip vinyl plank flooring with wood base. Low/No VOC adhesives and sealants. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  |  | 0
p | 6 | Replace existing flooring with ceramic tile and tile base. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0
MEP DISCIPLINES
| P | PLUMBING (GENERAL)
p | 1 | Expansion tank for building water heater, see water heater schedule and detail for more information. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  |  | 0
p | 2 | Building water heaters: 50 gallon = 0.92 EF 80 gallon = 0.89 EF | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  |  | 0
m | 3 | Plumbing Add/Alt: Remove and replace two RPZ backflow preventers on domestic water service entrance | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 4 | Plumbing: Provide full port shutoff valve at the base of each domestic riser to units. Typical all risers. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
m | 5 | Plumbing Add/Alt: Remove and replace hose bib. Typical for all hose bibs on exterior of building. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 6 | Hose Bibb: Add for exterior use / rated access panel added. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 7 | Remove and replace gas-fired water boiler and 500 gallon storage tank. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 8 | Water Softener - Domestic water booster pump: Provide booster pump (Fixture BP from P000) on DCW branch serving water softener and domestic water heating equipment. Reconnect water softener to treat water supply to domestic water heating equipment, provide bypass. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
m | 9 | Provide 3" Watts 957OSY RPZ backflow preventer on domestic water line after meter. Provide drainage piping to nearest floor drain with air gap fitting. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
EXTERIOR, COMMON AREAS & DWELLING UNITS
m | 10 | Inspect all existing natural gas mains and supply lines. Remove, repair, replace or clean as required. No deficiencies were identified in PCNA report. Provide allowance. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  |  | 0
m | 11 | Inspect all existing sanitary lines from building to street. Remove, repair, replace or clean as required. No deficiencies were identified in PCNA report. Provide allowance. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  |  | 0
COMMON AREAS & DWELLING UNITS
| 12 | All new domestic water supply piping shall be copper. Provide alternate pricing for CPVC | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
| 13 | Remove and replace all domestic shut-off valves | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
| 14 | All faucets to have lever handle and temperature limiting device that conforms to ASSE 1070 Kitchen faucets ≤ 2.0 gpf; Lavatory faucets ≤ 1.5 gpf & WaterSense label | Code Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
| 15 | Fire stop all new and existing pipe penetrations at fire rated ceiling/wall penetrations. | Code Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 16 | Install new low flow ADA compliant toilets. Provide American Standard Cadet 3 Right Height Elongated Toilet (1.28 GPF). Toilets ≤ 1.28 gpf & WaterSense label | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 17 | Reconfigure plumbing for new fixture locations as shown on drawings. Provide allowance for Remove and Replace of drywall ceilings below. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 18 | Remove and replace bathroom sinks and faucets. Faucets to have lever handle and temperature limiting device that conforms to ASSE 1070 Lavatory faucets ≤ 1.5 gpf & WaterSense label | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 19 | Remove and replace kitchen sinks and faucets. Faucets to have lever handle and temperature limiting device that conforms to ASSE 1070 Kitchen faucets ≤ 2.0 gpf; Lavatory faucets ≤ 1.5 gpf & WaterSense label | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 20 | Provide In-Sin-Erator Badger 5 disposal in units and for community room sink. | NCR Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 21 | Provide TrueBro "Lavguard" plumbing insulation for handicap accessible sinks and lavatories. | NCR Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
| M | HVAC (GENERAL)
p | 1 | Ductwork carrying conditioned air in pitched roof attics with enough space to allow access are insulated minimum R-Value of R8. | Architects Recommendation |  | 15 - Heat and Ventilation |  |  |  | 0
m | 2 | Dryer duct cover with plastic laminate storage shelf at laundry room | Architects Recommendation |  | 15 - Heat and Ventilation |  |  | 0 | 0
p | 3 | Remove and replace all heat pump units and air handlers completely - see mechanical drawings. Replacement heat pump shall be Energy Star Qualified | OHFA Design Standard |  | 15 - Heat and Ventilation |  |  | 0 | 0
p | 4 | New mechanical units Heat pumps shall be Energy Star Qualified. Cooling equipment ≥ 13 SEER | OHFA Design Standard |  | 15 - Heat and Ventilation |  |  |  | 0
| 5 | Condensing units to be bolted to concrete pads | Architects Recommendation |  | 15 - Heat and Ventilation |  |  | 0 | 0
p | 6 | Provide new filters for existing AHU's, connected to existing ductwork with new wall sleeves. Clean and flush entire condensate drain/riser. Heat Pump shall be Energy Star Qualified | OHFA Design Standard |  | 15 - Heat and Ventilation |  |  | 0 | 0
p | 7 | New exhaust fans connected to existing ductwork. Energy Star labeled. | OHFA Design Standard |  | 15 - Heat and Ventilation |  |  | 0 | 0
p | 8 | Relocate SAR | Architects Recommendation |  | 15 - Heat and Ventilation |  |  |  | 0
p | 9 | Provide new dwelling unit t-stats are 47" AFF | Code Requirement |  | 15 - Heat and Ventilation |  |  | 0 | 0
COMMON AREAS
p | 10 | Existing split system heat pump to remain. Provide new filters, clean coils, inspect systems and report and required repairs. No new duct work. Cooling equipment ≥ 13 SEER, Heat Pump shall be Energy Star Qualified. | OHFA Design Standard |  | 15 - Heat and Ventilation |  |  | 0 | 0
| E | ELECTRICAL (GENERAL)
p | 1 | Replace corridor wall lighting with wall sconces at unit entry doors and new strip lighting. Energy Star compliant | OHFA Design Standard | Included in Common Area Cost Above | 16 - Electrical |  |  | 0 | 0
m | 2 | Remove existing emergency call lights at unit entry doors and cover over with new wall finish to match adjacent wall finish, patch and repair. | Architects Recommendation |  | 16 - Electrical |  |  | 0 | 0
m | 3 | Provide new wall lighting with wall sconces at unit entry doors and surface mounted can lights. | Architects Recommendation |  | 16 - Electrical |  |  | 0 | 0
p | 4 | Remove and replace all lighting with new LED/Energy Star upgraded lighting package. | OHFA Design Standard | $400 per apartment unit, Common Area picked up above | 16 - Electrical |  |  | 0 | 0
p | 5 | Existing lighting fixtures shown to be demolished in common areas | Code Requirement |  | 16 - Electrical |  |  |  | 0
p | 6 | Remove and replace fire alarm devices | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
| 7 | Remove and replace fire suppression tamper switch/flow switch | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
p | 8 | Remove and replace existing emergency lights and exit signs | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
p | 9 | Provide time clock for ceiling light circuit, install time clocks next to electrical panels | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
p | 10 | Relocate disconnect switch for dwelling unit heat pumps, extend wiring from dwelling unit load centers. | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
p | 11 | Existing load center to remain, remove and replace all 15-amp and 20-amp breakers with arc-fault breakers. | Architects Recommendation | Per Unit (2) assumed | 16 - Electrical |  |  | 0 | 0
| 12 | Smoke detectors to be interconnected for communication | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
EXTERIOR
m | 13 | Remove and replace and upgrade all exterior security lighting. | Architects Recommendation |  | 16 - Electrical |  |  |  | 0
m | 14 | Remove and replace exterior building lighting with new upgraded Energy Star lighting package - Site lighting and Building lighting | Architects Recommendation |  | 16 - Electrical |  |  |  | 0
COMMON AREAS & DWELLING UNITS
p | 15 | Replace and upgrade existing common area interior lighting to LED surface mounted cans, and LED exit signs with generator backup. Verify exit lighting is adequate and operable, otherwise provide new fixtures by authority having jurisdiction. Energy Star lighting fixtures. | OHFA Design Standard | Included in Common Area Cost Above | 16 - Electrical |  |  | 0 | 0
p | 16 | In all public and dwelling unit rooms/spaces where wiring is being replaced, light switches, thermostats and other environmental controls are to be placed in accessible locations no higher than 48" AFF to top of device. and electrical receptacles, phone jacks and data ports are to be installed at 18" AFF | Code Requirement | Just for Common Areas | 16 - Electrical |  |  | 0 | 0
p | 17 | Provide GFI protected receptacles per NEC in HC unit kitchens | Code Requirement | Included | 16 - Electrical |  |  |  | 0
p | 18 | Remove and replace all common area and HC unit switches. With Rocker Type Switches | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
COMMON AREAS
p | 19 | Install "prop-open" alarms at new exterior corridor doors. | Architects Recommendation |  | 16 - Electrical |  |  | 0 | 0
m | 20 | Remove existing corridor emergency call indicator lights. | Architects Recommendation |  | 16 - Electrical |  |  | 0 | 0
p | 21 | Remove and replace, or install new magnetic door hold opens at all common area doors within fire rated assemblies connected to the building fire alarm system. | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
LIVING UNITS OVERVIEW
• (144) total units: (8) Existing One Bedrooms Units and (136) Existing Two Bedroom Units • Eight (8) existing units are designated Handicap and are currently non-compliant with accessibility standards. The eight (8) handicap accessible units will be partially demolished and restructured to provide code required access to the greatest extent structurally feasible. • Two (2) existing units are designated as Sensory Impaired units. These two units are to be renovated per the handicap detail scope. • The remaining Standard Units are to be renovated per the detail scope.
| LUD | LIVING UNIT DEMOLITION
UNITS B, C & D - ANSI TYPE-A, SI & UFAS 504
p | 1 | Remove exterior sliding patio door, door frame and door threshold, prep opening to receive new door. | Useful Life Duration Limit |  | 08 - Doors |  |  |  | 0
p | 2 | Remove door, door frame and door hardware completely. | Architects Recommendation |  | 08 - Doors |  |  |  | 0
p | 3 | Remove door, door frame and hardware completely, rough opening to be enlarged. See A300's and A701 for details. Bathrooms and Bedrooms. | Code Requirement |  | 08 - Doors |  |  |  | 0
p | 4 | Remove/Replace appliances | Code Requirement |  | 11 - Appliances |  |  |  | 0
p | 5 | Remove plumbing fixtures, see plumbing drawings. | Code Requirement |  | 15 - Plumbing and Hot Water |  |  |  | 0
p | 6 | Remove water heater, see plumbing drawings. | Code Requirement |  | 15 - Heat and Ventilation |  |  |  | 0
p | 7 | Remove air handling unit, see mechanical drawings. | Code Requirement |  | 15 - Air Conditioning |  |  |  | 0
p | 8 | Remove heat pump unit, see mechanical drawings. | Code Requirement |  | 15 - Heat and Ventilation |  |  |  | 0
p | 9 | Remove base and wall cabinets completely. | Code Requirement |  | 11 - Cabinets |  |  |  | 0
p | 10 | Remove countertop and backsplash completely. | Code Requirement |  | 11 - Cabinets |  |  |  | 0
p | 11 | Remove flooring finish completely down to gypcrete topping, gypcrete topping to be protected during demolition entire unit. | Code Requirement |  | 09 - Resilient Flooring |  |  |  | 0
p | 12 | Provide new door opening in bearing wall. Contractor to provide temporary shoring as required, see door schedule, see structural drawings for framing modifications. | Architects Recommendation |  | 08 - Doors |  |  |  | 0
p | 13 | Remove top rail. Secure balusters to be reused with new top rail. | Architects Recommendation |  | 06 - Finish Carpentry |  |  |  | 0
p | 14 | Remove existing partition walls for reconfiguration. See plan for reconfiguration. | Architects Recommendation |  | 09 - Drywall |  |  |  | 0
p | 15 | Remove and replace 40 LF of base in units. | Architects Recommendation |  | 09 - Resilient Flooring |  |  |  | 0
p | 16 | Remove unit entry doors and frames. Remove dwelling unit interior doors. | Architects Recommendation |  | 08 - Doors |  |  |  | 0
p | 17 | Bedroom and bathroom doors are to be removed, the opening enlarged and 3'-0" doors installed | Code Requirement |  | 08 - Doors |  |  |  | 0
p | 18 | Remove and replace kitchen cabinets and tops. | Code Requirement |  | 11 - Cabinets |  |  |  | 0
p | 19 | Remove and replace tub and tile surround. | Code Requirement |  | 09 - Tile Work |  |  |  | 0
p | 20 | Remove and replace bathroom VCT flooring and base trim. | Architects Recommendation |  | 09 - Resilient Flooring |  |  |  | 0
p | 21 | Remove and replace shower head. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  |  | 0
p | 22 | Remove and replace bathroom medicine cabinet. | Architects Recommendation |  | 11 - Cabinets |  |  |  | 0
p | 23 | Remove dwelling unit carpeting Insatll new | Architects Recommendation |  | 12 - Carpets |  |  |  | 0
p | 24 | Remove plastic laminate window sills. | Architects Recommendation |  | 08 - Windows |  |  |  | 0
p | 25 | Remove all closet shelf and rod | Architects Recommendation |  | 06 - Finish Carpentry |  |  |  | 0
p | 26 | Remove existing unit lighting. | Architects Recommendation |  | 16 - Electrical |  |  |  | 0
| LUD | LIVING UNIT DEMOLITION
UNITS A, B, C & E - ANSI TYPE-B
p | 27 | Remove appliances, see electrical drawings. | Code Requirement |  | 11 - Appliances |  |  |  | 0
p | 28 | Remove plumbing fixtures, see plumbing drawings. | Code Requirement |  | 15 - Plumbing and Hot Water |  |  |  | 0
p | 29 | Remove water heater, see plumbing drawings | Code Requirement |  | 15 - Heat and Ventilation |  |  |  | 0
p | 30 | Remove base and wall cabinets completely. | Code Requirement |  | 11 - Cabinets |  |  |  | 0
p | 31 | Remove countertop and backsplash completely. | Code Requirement |  | 11 - Cabinets |  |  |  | 0
p | 32 | Remove flooring finish completely down to gypcrete topping, gypcrete topping to be protected during demolition entire unit. | Code Requirement |  | 09 - Resilient Flooring |  |  |  | 0
p | 33 | Remove all closet shelf and rod | Architects Recommendation |  | 06 - Finish Carpentry |  |  |  | 0
p | 34 | Remove cabinet above refrigerator. Remove all doors and drawers in kitchen and bathroom cabinets. Remove all shelving in cabinets. Remove countertop with existing sink to provide adequate hole size for new sink. | Architects Recommendation |  | 11 - Cabinets |  |  |  | 0
p | 35 | Remove 40 LF of base in units. | Architects Recommendation |  | 09 - Resilient Flooring |  |  |  | 0
p | 36 | Remove entry doors, frames and hardware. | Architects Recommendation |  | 08 - Doors |  |  |  | 0
p | 37 | Remove countertop and backsplash completely. | Architects Recommendation |  | 11 - Cabinets |  |  |  | 0
| HCU | HANDICAP UNITS: ANSI 'A' & SI UNITS; & UFAS 504 UNITS
TOTAL # OF UNITS: (8)
SI UNITS
p | 1 | Units C & D: Provide new door opening in bearing wall. Contractor to provide temporary shoring as required, see door schedule, see structural drawings for framing modifications. | Code Requirement |  | 08 - Doors |  |  | 0 | 0
p | 2 | Replace all closet shelf and rod | Architects Recommendation |  | 06 - Finish Carpentry |  |  | 0 | 0
p | 3 | Provide new bathroom accessories | Architects Recommendation |  | 11 - Special Equipment |  |  | 0 | 0
GENERAL
p | 4 | Correct interior accessibility issues | Code Requirement |  | 06 - Rough Carpentry |  |  | 0 | 0
p | 5 | 5 linen shelves, equally spaced, hold top shelf 24" from ceiling | Architects Recommendation |  | 10 - Specialities |  |  | 0 | 0
| 6 | Include provisions to repair all damaged existing drywall within the living units 20 SF allowance per unit. | Architects Recommendation |  | 09 - Drywall |  |  |  | 0
p | 7 | Repair select peeling drywall tape at unit ceiling/wall transitions. Provide allowance. | Architects Recommendation |  | 09 - Drywall |  |  |  | 0
| 8 | Reconfigure entry/closet for accessibility with 18" clear from wall to door latch. | Code Requirement | Included in cost above | 06 - Rough Carpentry |  |  | 0 | 0
p | 9 | Caulk and seal entire perimeter of units walls at the floor/base. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Drywall |  |  |  | 0
p | 10 | Wall mounted package shelves - clarified: to be installed at all dwelling unit entry doors. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 06 - Finish Carpentry |  |  | 0 | 0
p | 11 | Include gypsum board wall and ceiling repair at existing wall base location, new flooring, base throughout, paint all walls and ceilings, and new shelving throughout. Assume 40 SF of repair. | Architects Recommendation |  | 09 - Drywall |  |  |  | 0
p | 12 | Provide 40 LF of base trim replacement in units. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0
p | 13 | Lower the elevation of thermostats in all units. Repair gypsum board at location. | Code Requirement |  | 15 - Heat and Ventilation |  |  | 0 | 0
p | 14 | All kitchen and bathroom cabinets in units to receive new toe kick board. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 11 - Cabinets |  |  |  | 0
p | 15 | Install new painted wood base with ogee base profile. | Architects Recommendation |  | 09 - Resilient Flooring |  |  |  | 0
p | 16 | Replace window sills with cultured marble. Low/No VOC adhesives and sealants. | Architects Recommendation |  | 08 - Windows |  |  |  | 0
p | 17 | New Anti-Scald protection over all supply/drain piping. | Code Requirement |  | 15 - Plumbing and Hot Water |  |  |  | 0
p | 18 | Replace all appliances with Client Standard black Whirlpool appliances. Appliances to be Energy Star labeled. | OHFA Design Standard |  | 11 - Appliances |  |  | 0 | 0
p | 19 | Repaint 100% of all unit areas. Use Low/No VOC paints and primers. | OHFA Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0
p | 20 | Replace carpet with laminated vinyl plank flooring. Assume 50 SF of gypcrete repair. Low/No VOC adhesives and sealants. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0
DOORS
p | 21 | Replace unit entry doors and frames with new 20-minute rated doors. Patch and repair walls as required. Base bid - existing door frame to be reused and painted in field. Add/Alternate - Replacement of all common area door frames. | Code Requirement |  | 08 - Doors |  |  | 0 | 0
p | 22 | Bedroom and bathroom doors are to be removed, the opening enlarged and 3'-0" doors installed | Code Requirement |  | 08 - Doors |  |  | 0 | 0
p | 23 | Replace all interior doors and frames with filled core flush wood doors. Paint to match trim. Low/No VOC paints and primers. | OHFA Design Standard |  | 08 - Doors |  |  | 0 | 0
p | 24 | Install new unit door combination knocker/peep hole; HC units to receive Hi-Low. Install door bell at height for seated person. Replace all door hardware with Schlage 'AL' series with Neptune lever handle design. | Code Requirement |  | 08 - Doors |  |  | 0 | 0
p | 25 | Remove and replace all unit entry door hardware with KABA Rezsheild lock and passage lever handset. | Architects Recommendation |  | 08 - Doors |  |  | 0 | 0
p | 26 | Install new unit door combination knocker/peep hole; HC units to receive Hi-Low. | Architects Recommendation |  | 08 - Doors |  |  |  | 0
p | 27 | Remove and replace bedroom door and frame. Enlarge opening for 36” door. | Code Requirement |  | 08 - Doors |  |  |  | 0
KITCHEN
p | 28 | New wall and base cabinets, countertops and backsplash. Low/No Formaldehyde emitting wood products. | OHFA Design Standard | Observed at dwelling unit 137. | 11 - Cabinets |  |  |  | 0
p | 29 | Provide shield behind new range | Architects Recommendation |  | 07 - Sheet Metal |  |  | 0 | 0
p | 30 | Kitchen to meet current ANSI unit type 'A' and 'B' requirements as permitted by existing physical conditions. | Code Requirement |  | 01 - General Requirements |  |  |  | 0
p | 31 | Reconfigure kitchen as shown on drawings. | PCNA 2017, Accessibility | 1-BR and 2-BR dwelling units. | 11 - Cabinets |  |  |  | 0
p | 32 | Install non-slip vinyl flooring (and base) extended under all removable equipment and removable cabinetry to walls. | Code Requirement | In Cost above | 09 - Resilient Flooring |  |  |  | 0
p | 33 | Install kitchen cabinets with wire pulls. Base cabinets to be 32" HC accessible with rollout shelving. Top of bottom roll-out shelf installed 15" minimum above finish floor. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 11 - Cabinets |  |  | 0 | 0
| 34 | Install plastic laminate countertops with molded edges and separate 6" backsplash. Lower outlets and install in backsplash. Low/No Formaldehyde emitting wood products. | OHFA Design Standard | In Cost above | 11 - Cabinets |  |  | 0 | 0
p | 35 | Install plastic laminate counter work space with plastic laminate shelving above at opposite side of cabinets at location shown on drawings. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 11 - Cabinets |  |  |  | 0
p | 36 | Install ADA compliant 33" double bowl sink with lever faucet. Insulate plumbing. Kitchen faucets ≤ 2.0 gpf | Code Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 37 | Install frost free refrigerator. | NCR Design Standard |  | 11 - Appliances |  |  |  | 0
p | 38 | Install 30" electric self-cleaning drop-in range with front controls; window and over light; Provide full height backsplash to match range. Grease shield to be baked on enamel finish over steel to match color of range or satin finished stainless steel with matching screws. | Code Requirement |  | 11 - Appliances |  |  |  | 0
p | 39 | Provide range hood with fire canisters. | NCR Design Standard | Included in cost above | 11 - Appliances |  |  | 0 | 0
p | 40 | Existing soffit exhaust vent to remain. | Architects Recommendation |  | 01 - General Requirements |  |  |  | 0
p | 41 | Install new disposal | NCR Design Standard |  | 11 - Appliances |  |  | 0 | 0
m | 42 | Install under cabinet mount task lighting. | NCR Design Standard |  | 16 - Electrical |  |  | 0 | 0
p | 43 | Install 4" vinyl cove base. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  |  | 0
p | 44 | Replace kitchen flooring with new vinyl plank and base. Low/No VOC adhesives and sealants. | OHFA Design Standard | Included in cost above | 09 - Resilient Flooring |  |  | 0 | 0
KITCHEN / BATHROOM
p | 45 | Plastic laminate countertops included (solid surface excluded). Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 11 - Cabinets |  |  |  | 0
p | 46 | Provide plastic laminate countertop with 4" backsplash and side splash (6" splash at HC units). Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 11 - Cabinets |  |  |  | 0
BATHROOM
p | 47 | Provide new bathroom accessories | NCR Design Standard |  | 10 - Specialities |  |  | 0 | 0
p | 48 | Remove tub and surround. Install ½” beveled threshold 60” clear roll in type prefabricated fiberglass shower unit with ADA compliant grab bars, control valves and wand/slidebar locations at all HC units. | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 49 | New sink basin as specified - insulate all exposed plumbing as required for anti-scald on hot water supply and waste. Lavatory faucets ≤ 1.5 gpf & WaterSense label | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 50 | Install 1/2" beveled threshold 63" clear roll in type prefabricated fiberglass shower unit with ADA compliant grab bars, controls and wand/slide bar locations at all HC units. | Code Requirement |  | 11 - Special Equipment |  |  |  | 0
p | 51 | Install solid blocking at rear and side wall of toilet. Install flip-down grab bar at side wall and 36" grab bar at rear wall where sidewall grab bars are not feasible. | Code Requirement |  | 06 - Rough Carpentry |  |  | 0 | 0
p | 52 | Install low flow 17" to 19" ADA compliant toilet Toilets ≤ 1.28 gpf & WaterSense label | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 53 | Install plastic laminate wall hung vanity - provide 30" minimum clear open space centered on sink. Top of countertop to be 34" maximum to top rim of sink. Low/No Formaldehyde emitting wood products. | Code Requirement | Parallel approach not achieved at existing bathroom configuration. Use base cabinets with removable fronts or roll under vanity tops. | 11 - Cabinets |  |  | 0 | 0
| 54 | Install new recessed shop or field fabricated custom medicine cabinet with door. | NCR Design Standard | Included in cost above | 10 - Specialities |  |  | 0 | 0
p | 55 | Modify existing closet to add shelving with wood swing door opening to bathroom. Bottom shelf installed 42" AFF. (HC unit only). Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 06 - Finish Carpentry |  |  | 0 | 0
| 56 | Paint all bathrooms. Low/No VOC paints and primers. | OHFA Design Standard | Included in cost above | 09 - Painting and Decorating |  |  | 0 | 0
p | 57 | Install floor drain in HC unit bathroom. | Architects Recommendation |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
| 58 | Remove and replace bathroom VCT flooring with new ceramic tile flooring with tile base. Low/No VOC adhesives and sealants. | OHFA Design Standard | Included in cost above | 09 - Resilient Flooring |  |  | 0 | 0
p | 59 | Provide non-lighted mirrored medicine cabinet. | NCR Design Standard |  | 11 - Special Equipment |  |  |  | 0
p | 60 | Replace shower head and controls as well as shower valves | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 61 | Grab bars: new grab bars to be installed at all existing dwelling unit tub enclosures. | Code Requirement |  | 11 - Special Equipment |  |  |  | 0
BEDROOM
p | 62 | Remove and replace bedroom closet shelving with new adjustable height hardware wire system. | Architects Recommendation |  | 06 - Finish Carpentry |  |  | 0 | 0
UNIT FINISHES
p | 63 | Replace unit carpeting with new direct glue-down. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 12 - Carpets |  |  |  | 0
p | 64 | Install new non-slip vinyl flooring with base to limits shown on drawings. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  |  | 0
p | 65 | Remove and replace all 4" vinyl base. Install new pre-finished wood wall base in unit living/dining, bedrooms and closets at all carpeted areas. Install new vinyl tile flooring with 4" vinyl cove at kitchen. Remove and replace 40 L.F. of existing vinyl base. Low/No VOC adhesives and sealants. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  |  | 0
p | 66 | Install new non-slip vinyl flooring with base shown on drawings. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  |  | 0
p | 67 | Door frames to be painted. Low/No VOC paints and primers. | OHFA Design Standard |  | 09 - Painting and Decorating |  |  |  | 0
p | 68 | Install new painted wood base with ogee base profile. Low/No VOC paints and primers. Low/No VOC adhesives and sealants. Low/No Formaldehyde emitting wood products. | OHFA Design Standard |  | 09 - Wood Flooring |  |  |  | 0
PLUMBING (HC UNITS / DWELLINGS)
| 1 | Plumbing fixture controls to be lever operated | Code Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 2 | Electric domestic water heater Unit water heaters - 40 gallon = 0.93 EF | OHFA Design Standard | Observed cabinet damage at Dwelling Unit 137 | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 3 | HC Units: Provide 36" x 64" Clarion roll-in showers with pressure balancing valve conforming to ASSE 1016 | NCR Design Standard |  | 15 - Plumbing and Hot Water |  |  |  | 0
p | 4 | HC Units: Install new floor drain in bathroom. Provide allowance for Remove and Replace of drywall ceilings below. | NCR Design Standard |  | 15 - Plumbing and Hot Water |  |  |  | 0
MECHANICAL (HC UNITS / DWELLINGS)
p | 1 | New mechanical units Cooling equipment ≥ 13 SEER, Heat Pump shall be Energy Star Qualified. | OHFA Design Standard | PCNA Immediate Repair noted for clogged drain line. | 15 - Air Conditioning |  |  |  | 0
| 2 | All new equipment to be labeled 'Energy Star' compliant | OHFA Design Standard |  | 15 - Air Conditioning |  |  | 0 | 0
p | 3 | Existing systems consist of ducted split system heat pumps with wall mounted air-handling units. Remove and replace split system heat pumps, refrigerant piping, controls, etc. Existing soffit mounted ductwork and/or air devices to be modified to newly configured dwelling units. | Architects Recommendation |  | 15 - Air Conditioning |  |  |  | 0
p | 4 | Provide new large digital display thermostat, mounted at 47 inches AFF at top of thermostat. | Code Requirement | PCNA reported that existing thermostats not at accessible heights. | 15 - Air Conditioning |  |  | 0 | 0
p | 5 | Route refrigerant piping within mechanical closets to pad mounted heat pump condensing units, at grade. Cooling equipment ≥ 13 SEER | OHFA Design Standard |  | 15 - Air Conditioning |  |  |  | 0
p | 6 | Remove and replace existing bathroom exhaust fan with Energy Stat rated exhaust fan. Existing exhaust ductwork to remain. | OHFA Design Standard |  | 15 - Air Conditioning |  |  | 0 | 0
ELECTRICAL (HC UNITS / DWELLINGS)
p | 1 | Existing load centers to remain; remove and replace 15amp and 20amp breakers in existing load centers: Locations Vary. Provide arc fault protection for all new circuits and existing circuits. Provide GFI protected receptacles in kitchens and bathroom. New outlets spaced according to NEC. | Architects Recommendation |  | 16 - Electrical |  |  |  | 0
p | 2 | Remove and replace all HC unit lighting with new Energy Star rated fixtures. | NCR Design Standard |  | 16 - Electrical |  |  | 0 | 0
p | 3 | Install new switched ceiling fan/light combo in bedroom. Energy Star fixtures. | OHFA Design Standard |  | 16 - Electrical |  |  | 0 | 0
p | 4 | Remove and replace appliances, see electrical drawings. | Useful Life Duration Limit |  | 16 - Electrical |  |  |  | 0
p | 5 | Install in HC dwelling units tamper resistant receptacles per NEC. Provide AFCE protection per NEC. | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
p | 6 | Install visual/audible alarm devices in HC unit and Sensory Impaired unit living rooms, bedrooms and bathrooms. | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
| SU | STANDARD LIVING UNITS - ANSI 'B' Units
TOTAL # OF UNITS: (136)
GENERAL
| 1 | Unit layouts will not be reconfigured | Code Requirement | 1-BR and 2-BR dwelling units have accessibility issues at kitchen. Reconfiguration is recommended or replacement of standard refrigerators with counter depth appliances is recommended. | 01 - General Requirements |  |  | 0 | 0
p | 2 | Replace all closet shelf and rod units. | Architects Recommendation |  | 06 - Finish Carpentry |  |  | 0 | 0
p | 3 | Correct interior accessibility issues | Code Requirement |  | 06 - Rough Carpentry |  |  | 0 | 0
p | 4 | Patch and repair drywall | Architects Recommendation |  | 09 - Drywall |  |  |  | 0
p | 5 | Paint 100% of walls and ceilings, assume 20 SF/dwelling unit of patch and repair work. Low/No VOC paints and primers. | OHFA Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0
p | 6 | Cabinets/Countertops at dwelling units: Existing cabinets to remain. Replace all doors and drawers in kitchen and bathroom cabinets. Replace all shelving in cabinets. Replace countertop with existing sink to provide adequate hole size for new sink. | Architects Recommendation |  | 11 - Cabinets |  |  | 0 | 0
p | 7 | Replace all appliances with Client Standard black Whirlpool Energy Star appliances. | NCR Design Standard |  | 11 - Appliances |  |  | 0 | 0
p | 8 | Include gypsum board wall and ceiling repair at existing wall base location, new flooring, base throughout, paint all walls and ceilings, and new shelving throughout. Assume 40 SF of repair. | Architects Recommendation |  | 09 - Drywall |  |  |  | 0
p | 9 | Replace 40 LF of base in units. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0
p | 10 | Lower the elevation of thermostats in all units. Repair gypsum board at location. | Code Requirement |  | 15 - Heat and Ventilation |  |  | 0 | 0
| 11 | All kitchen and bathroom cabinets in units to receive new toe kick board. | Architects Recommendation | Inluded in Cost Above | 11 - Cabinets |  |  | 0 | 0
p | 12 | Caulk and seal entire perimeter of units walls at the floor/base. Low/No VOC adhesives and sealants. | Architects Recommendation |  | 09 - Resilient Flooring |  |  |  | 0
p | 13 | Replace all appliances with Client Standard white Whirlpool Energy Star appliances. | NCR Design Standard |  | 11 - Appliances |  |  |  | 0
p | 14 | New Anti-Scald protection over all supply/drain piping. | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  |  | 0
DOORS
p | 15 | Replace unit entry doors and hardware new 20-minuted rated doors. Base bid - existing door frame to be reused and painted in field. Add/Alternate - Replacement of all common area door frames. HC units to receive Hi-Low peep hole with knocker. Door hardware with KABA Rezshield lock and passage lever handset. Patch and repair walls as required. | Architects Recommendation |  | 08 - Doors |  |  | 0 | 0
p | 16 | Wall mounted package shelves - clarified: to be installed at all dwelling unit entry doors. | NCR Design Standard |  | 10 - Specialities |  |  | 0 | 0
p | 17 | Remove and replace all unit entry door hardware with KABA Rezsheild lock and passage lever handset. | Architects Recommendation |  | 08 - Doors |  |  |  | 0
p | 18 | Install new unit door combination knocker/peep hole; HC units to receive Hi-Low. | Architects Recommendation |  | 08 - Doors |  |  | 0 | 0
p | 19 | Remove and replace all dwelling unit interior door hardware. | Architects Recommendation |  | 08 - Doors |  |  | 0 | 0
KITCHEN
p | 20 | Provide and install new energy star Frigidaire 16.3 CU FT | Useful Life Duration Limit | Previous scope did not identify NCR standard Whirlpool refrigerators. | 11 - Appliances |  |  |  | 0
p | 21 | Provide new range, refrigerator and dishwasher. To be Energy Star labeled. | Useful Life Duration Limit |  | 11 - Appliances |  |  |  | 0
p | 22 | Provide shield behind new range | Architects Recommendation |  | 05 - Metals |  |  | 0 | 0
p | 23 | Kitchen to meet current ANSI unit type 'A' and 'B' requirements as permitted by existing physical conditions. | Code Requirement |  | 06 - Rough Carpentry |  |  | 0 | 0
p | 24 | Replace kitchen flooring with new vinyl plank and base. Low/No VOC adhesives and sealants. | NCR Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0
KITCHEN / BATHROOM
m | 25 | Base and wall cabinets to remain where in good condition and no accessibility violations are existing. | PCNA 2017, Accessibility | Observed cabinet damage at Dwelling Unit 137 | 11 - Cabinets |  |  | 0 | 0
p | 26 | Provide plastic laminate countertop with 4" backsplash and side splash (6" splash at HC units) | NCR Design Standard |  | 11 - Cabinets |  |  |  | 0
BATHROOM
p | 27 | New sink basin as specified - insulate all exposed plumbing as required for anti-scald on hot water supply and waste. Kitchen faucets ≤ 2.0 gpf | OHFA Design Standard | Parallel approach not achieved at existing bathroom configuration. Use base cabinets with removable fronts or roll under vanity tops. | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 28 | Provide new bathroom accessories | NCR Design Standard |  | 11 - Special Equipment |  |  | 0 | 0
p | 29 | Remove and replace bathroom VCT flooring with new vinyl flooring. Low/No VOC adhesives and sealants. | NCR Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0
| 30 | Remove lighted bathroom medicine cabinet. Provide non-lighted mirrored cabinet. | NCR Design Standard | Included in cost above | 10 - Specialities |  |  | 0 | 0
p | 31 | Remove and replace shower head with low flow fixture; install aerators on existing kitchen and lavatory faucets, replace shower valves | NCR Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
| 32 | Grab bars: new grab bars to be installed at all existing dwelling unit tub enclosures. | Code Requirement | Included in cost above | 10 - Specialities |  |  | 0 | 0
| UF | UNIT FINISHES - ALL
p | 1 | Replace flooring according to the finish schedule. Assume 50 S.F. gypcrete replacement in all units. Low/No VOC adhesives and sealants. | OHFA Design Standard |  | 09 - Resilient Flooring |  |  |  | 0
MEP DISCIPLINES
| P | PLUMBING
| 1 | Plumbing fixture controls to be lever operated | Code Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 2 | Electric domestic water heater Unit water heaters - 40 gallon = 0.93 EF | OHFA Design Standard | Observed at Dwelling Unit 326. | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 3 | New sink basin as specified - insulate all exposed plumbing as required for anti-scald on hot water supply and waste. Kitchen faucets ≤ 2.0 gpf | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  |  | 0
p | 4 | Fiberglass shower unit with factory installed grab bars - general contractor to coordinate exact dimensions with shower manufacturer. Showerheads ≤ 2.0 gpf & WaterSense label | OHFA Design Standard |  | 15 - Plumbing and Hot Water |  |  |  | 0
p | 5 | Electric domestic water heater Unit water heaters - 40 gallon = 0.93 EF | OHFA Design Standard | Observed cabinet damage at Dwelling Unit 137 | 15 - Plumbing and Hot Water |  |  |  | 0
| M | HVAC
| 1 | R/R four pipe system | PCNA 2019 | [5 empty] | ???
p | 1 | New mechanical units Cooling equipment ≥ 13 SEER, Heat Pump shall be Energy Star Qualified | Useful Life Duration Limit | PCNA Immediate Repair noted for clogged drain line. | 15 - Heat and Ventilation |  |  |  | 0
p | 2 | Remove and replace recessed fan coil unit | Useful Life Duration Limit |  | 15 - Heat and Ventilation |  |  |  | 0
| 3 | All new equipment to be labeled 'Energy Star' compliant | OHFA Design Standard |  | 15 - Air Conditioning |  |  | 0 | 0
p | 4 | Existing systems consist of ducted split system heat pumps with wall mounted air-handling units. Remove and replace split system heat pumps, refrigerant piping, controls, etc. Existing soffit mounted ductwork and/or air devices to be modified to newly configured dwelling units. | Architects Recommendation |  | 15 - Air Conditioning |  |  |  | 0
p | 5 | Provide new large digital display thermostat, mounted at 47 inches AFF at top of thermostat. | Code Requirement | PCNA reported that existing thermostats not at accessible heights. | 15 - Air Conditioning |  |  | 0 | 0
p | 6 | Route refrigerant piping within mechanical closets to pad mounted heat pump condensing units, at grade. Cooling equipment ≥ 13 SEER | OHFA Design Standard |  | 15 - Air Conditioning |  |  |  | 0
p | 7 | Remove and replace existing bathroom exhaust fan with Energy Stat rated exhaust fan. Existing exhaust ductwork to remain. | OHFA Design Standard |  | 15 - Air Conditioning |  |  | 0 | 0
| E | ELECTRICAL
p | 1 | Existing load centers to remain; remove and replace 15amp and 20amp breakers in existing load centers: Locations Vary. Provide arc fault protection for all new circuits and existing circuits. Provide GFI protected receptacles in kitchens and bathroom. New outlets spaced according to NEC. | Architects Recommendation |  | 16 - Electrical |  |  |  | 0
p | 2 | Remove and replace all standard unit lighting with new Energy Star rated fixtures. | NCR Design Standard |  | 16 - Electrical |  |  | 0 | 0
p | 3 | Install new switched ceiling fan/light combo in bedroom. Energy Star fixtures. | OHFA Design Standard |  | 16 - Electrical |  |  | 0 | 0
p | 4 | Remove and replace appliances, see electrical drawings. | Useful Life Duration Limit |  | 16 - Electrical |  |  |  | 0
p | 5 | Install in stadard units tamper resistant receptacles per NEC. Provide AFCE protection per NEC. | Code Requirement |  | 16 - Electrical |  |  |  | 0
| RA | RADON ALLOWANCE
p | 1 | Remove and replace portion of concrete slab on grade as required for radon pit construction and routing of soil gas piping, dowel into existing slab and replace vapor barrier and concrete slab on grade to be flush with existing concrete slab. This scope only to be completed in units requiring radon pipes. | Funding Agent Requirement |  | 13 - Special Construction |  |  | 0 | 0
| BS | BUILDING SECURITY/ACCESS CONTROL
p | 1 | All exterior building entrance doors shall be secured with Grade 1 locksets. The main entrance shall be equipped with new by-parting aluminum entry system doors. Outer doors shall be activated via motion sensor. Inner doors shall be secured with FOB access. Visitors can be admitted into the building remotely from the Manager's Office or a resident unit. A visitor would notify either the office or living unit through the entrance telephone access system to gain admittance. Additionally, a visual display of the visitor will be provided to a display at the Manager's Office and via television within individual Dwelling Units. The door security system shall be programmable by the building manager via a personal computer. | Architects Recommendation |  | 08 - Doors |  |  | 0 | 0
m | 2 | Remove and replace existing visitor intercom system with new No-Phone bill Telephone Access system. Install at existing main entry vestibule. | NCR Design Standard |  | 16 - Electrical |  |  | 0 | 0
m | 3 | Provide keyless entry FOB system at building main entry interior vestibule door and exterior rear door to patio. | NCR Design Standard |  | 16 - Electrical |  |  | 0 | 0
p | 4 | Remove and replace HC push pads and auto openers at exterior and interior main entry vestibule storefront doors. Install new HC push pads and automatic door openers at 1st floor existing exterior rear storefront doors. | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
m | 5 | Install "prop-open" alarm system at all exterior stairwell doors, loading dock door and floor patio doors addressable to Manager's Office. | NCR Design Standard |  | 16 - Electrical |  |  | 0 | 0
| FP | FIRE/SMOKE PROTECTION
p | 1 | Replace fire suppression dry system piping. Remove and replace existing NFPA-13 dry fire sprinkler system and system components. | PCNA 2017, Accessibility | PCNA Immediate Repair due to incomplete inspections of fire alarm and sprinkler systems. | 15 - Plumbing and Hot Water |  |  | 0 | 0
p | 2 | Remove and replace automatic fire detection system with new addressable fire alarm system in mechanical room with new annunciator panel at entry vestibule. System and annunciation per NFPA 72. | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
p | 3 | Remove all wired smoke detectors and replace with hard-wired detectors in non-HC units and system detectors in HC and Sensory Impaired units, connected to the emergency call system so that unaddressed issues can be programmed to escalate and alert monitoring agency, management and/or fire department as required by authority having jurisdiction. Install smoke detectors within all bedrooms. In sensory impaired and HC units smoke detectors will have a 520 Hz sounder bases and strobe lights in the living room/restrooms, and a 177 CD strobe in the bedroom. Remove and replace smoke detectors in all common, administrative, maintenance, mechanical and storage areas. All smoke detectors shall be permanently connected to primary and secondary power supplies and installed per NFPA 72. | Code Requirement |  | 16 - Electrical |  |  | 0 | 0
p | 4 | Remove and replace smoke detectors in all common, administrative, maintenance, mechanical and storage areas. All smoke detectors shall be permanently connected to primary and secondary power supplies and installed per NFPA 72. | Code Requirement |  | 16 - Electrical |  |  |  | 0
p | 5 | Remove surface mounted fire extinguisher and hanging hardware completely. | NCR Design Standard | Owner to confirm scope. | 15 - Plumbing and Hot Water |  |  |  | 0
| EV | ELEVATOR
p | 1 | Elevator equipment, ADA controls and interior finish upgrade modernization to be included; provide stair lift for duration of time that the elevator will be out of service. | Useful Life Duration Limit |  | 14 - Elevators |  |  | 0 | 0
Scope Questions / Clarifications:
[6 empty] | Number of Units |  |  | 144 | 144 | 144 | 144 | 144
[6 empty] | Construction Budget |  |  | 6500000 | 100000 | 0 | 0 | 0
[6 empty] | Subtotal construction cost |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 6% safe harbor general conditions |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 2% safe harbor overhead |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 6% safe harbor fee |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | P&P bond |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | Builders risk (assumed to be by Owner) |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | Cost per unit Goal |  |  | 45138.8889 | 10000
[6 empty] | Cost per unit |  |  | 0 | 0 | 0 | 0 | 0

## Trade Item
TI: Pick from Menu | Sum from SCOPE
01 - General Requirements | 0
02 - Earth Work | 0
02 - Lawns and Plantings | 0
02 - Roads and Walks | 0
02 - Site Improvements | 0
02 - Site Utilities | 0
02 - Unusual Site Condition | 0
03 - Concrete | 0
04 - Masonry | 0
05 - Metals | 0
06 - Finish Carpentry | 0
06 - Rough Carpentry | 0
07 - Insulation | 0
07 - Roofing | 0
07 - Sheet Metal | 0
07 - Waterproofing | 0
08 - Doors | 0
08 - Glass | 0
08 - Windows | 0
09 - Acoustical | 0
09 - Drywall | 0
09 - Lath and Plaster | 0
09 - Painting and Decorating | 0
09 - Resilient Flooring | 0
09 - Tile Work | 0
09 - Wood Flooring | 0
10 - Specialities | 0
11 - Appliances | 0
11 - Cabinets | 0
11 - Special Equipment | 0
12 - Blinds and Shades, Artwork | 0
12 - Carpets | 0
13 - Special Construction | 0
14 - Elevators | 0
15 - Air Conditioning | 0
15 - Heat and Ventilation | 0
15 - Plumbing and Hot Water | 0
16 - Electrical | 0
0

## Origin of Scope
OoS: Pick from Menu
Code Requirement
Green Requirement
Useful Life Duration Limit
OHFA Design Standard
NCR Design Standard
Due Diligence
Design Element
Architects Recommendation
PCNA 2017, Accessibility
Funding Agent Requirement
Phase 1
-
-

## File Info
Creator | This chart was modified/created by Tony Killian. If you are having issues, he would be the first to ask concerning a resolution.
Locked Cell Password | -