## PROJECT INFO
National Church Residences
Commons at Grant |  | Most Recent Edit/Update | 2024-07-22
398 South Grant Avenue, Columbus, Ohio 43215 |  | Today's Date/Print Date | 2024-07-30
REHABILITATION WORK SCOPE ‐ DRAFT
PROJECT SUMMARY
Commons at Grant Senior Housing is an existing 100 unit 4-story affordable senior independent-living apartment building located in Columbus, Ohio, and constructed in 2003. The proposed renovation of Commons at Gran Senior Housing includes site, exterior, and interior common area and dwelling unit improvements. The proposed renovation will be completed in phases. The proposed site, exterior façade, and the common area renovation work are to be completed concurrently. The following describes the proposed scope of work.
EXISTING DEVELOPMENT
• One four-story, senior independent living apartment building set on 1.21 acres. • One-hundred (100) total units with seventy-seven (77) efficiency standard rental units, ten (10) efficiency units designated for Handicap accessibility, two (2) efficiency units designated for sight and visual impairment, and eleven (11) efficiency standard units. • 28 existing parking spaces which include two (2) spaces designated for handicap accessibility at grade.
WORK SCOPE SUMMARY
Unless otherwise indicated due to structural impracticality of existing conditions, all new construction shall be congruent with current Accessibility Standards and OHFA Universal Design Features to the greatest extent possible. Appliances, mechanical systems and lighting to be Energy Star rated - OHFA Sustainability Overlay for Rehabilitation Requirement. All paints, primers, adhesives, sealants, composite wood products and flooring are to meet OHFA Sustainability Overlay for Rehabilitation Requirements. Reference the Property Condition Assessment and Asbestos-Containing Material Operations & Maintenance Program Report for more detailed information. R/R = Remove and Replace Sustainable Design Requirements This Project will be developed to meet OHFA Sustainabilty Overlay for Rehabilitaion Requirement and will meet all prerequisite requirements as well as select elective credits.
KEY:
Priority (P)
Maybe (M)
No (N)
Removed from Pricing (VE)

## SCOPE
DATE |  | PROGRAM |  |  |  |  | PRICING
|  | CODE | ROOM | (P)CNA Item | Origin of Scope | Remarks | Trade Item | Quantity: Area | Quantity: Count | Price Per Unit | Budget Expectations - Auto | Budget Goal - Manual | VE (MM/DD/YYYY) | VE (MM/DD/YYYY) | VE (MM/DD/YYYY)
|  | EV | ENVIRONMENTAL
X | P | 1 | Passive radon mitigation systems. |  | [Funding Agency i.e. HUD] Design Standard |  | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
X | P | 2 | Enterprise Green Communities Certification |  | Green Requirement | SOL consultant | Pick from Menu |  |  | 0 | 0 | 0
X | N | 3 | No known ACM or lead based paint have been detected at this location per the Phase I. |  | Phase 1 Report |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
|  | S | SITE
Parking
X | P | 1 | Mill and overlay existing parking lot. (13,200 s.f.) |  | Useful Life Duration Limit |  | 02 - Roads and Walks |  |  | 0 | 0 | 0
X | P | 2 | Pavement seal and restripe parking spaces. |  | Useful Life Duration Limit |  | 02 - Roads and Walks |  |  |  | 0 | 0
X | P | 3 | (2) HC parking spaces to be provided including 1 van accessible space; code compliance of proposed locations to be verified. • Restripe parking as shown on plans to accommodate accessible parking. • Install tactile warning strips at all parking / drive flush transitions as shown on drawings. • Provide HC parking signage. |  | Code Requirement |  | 02 - Roads and Walks |  |  | 0 | 0 | 0
X | P | 4 | Pavement seal and restripe parking spaces. |  | Useful Life Duration Limit |  | 02 - Roads and Walks |  |  |  | 0 | 0
X | P | 5 | Install accessible path to the exterior dumpster enclosure |  | Code Requirement |  | 02 - Roads and Walks |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Concrete Flatwork
X | P | 6 | R/R concrete walks, curbing and ramps that border parking lot. See plan. • R/R adjacent sidewalks to meet accessible slopes and configure spaces to meet current accessibility. Concrete walk to be modified as required to permit code compliant slopes. • Finish to match existing. |  | Code Requirement |  | 02 - Roads and Walks |  |  | 0 | 0 | 0
X | P | 7 | R/R select areas of cracked or uneven stretches of concrete walk. |  | Due Diligence |  | 02 - Roads and Walks |  |  | 0 | 0 | 0
X | P | 8 | R/R or Install concrete joint sealant at control joints, cracks and abutments at existing sidewalks/ patios. |  | Due Diligence |  | 02 - Roads and Walks |  |  | 0 | 0 | 0
X | P | 9 | Regrade front entrance curb cut to allow for code compliant flush entry. |  | Code Requirement |  | 02 - Roads and Walks |  |  | 0 | 0 | 0
X | P | 10 | Grind concrete walk “trippers” at existing walks and patios that are to remain. A tripper is defined as a variance in height of more than ½” between adjoining slabs. Provide allowance for 2% of total existing concrete walk and patio areas shown on plans. |  | Code Requirement |  | 02 - Roads and Walks |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Landscaping
X | M | 11 | Inspect and clean all existing parking and yard catch basins/drains. Re-grade around inlet as required and re-seed. |  | Due Diligence |  | 02 - Site Improvements |  |  | 0 | 0 | 0
X | P | 12 | All disturbed areas on the site shall be seeded. |  | Due Diligence |  | 02 - Lawns and Plantings |  |  | 0 | 0 | 0
X | P | 13 | Manicure/prune and trim all existing trees. Provide min. distance from exterior face of building to bushes. |  | Due Diligence |  | 02 - Lawns and Plantings |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Utilities
X | P | 14 | R/R all existing light poles with new poles and LED fixtures in parking lot. |  | Pick from Menu | Verify fixtures amount | Pick from Menu |  |  | 0 | 0 | 0
X | M | 15 | Owner to inspect all underground roof drainage conduit. Contractor to clear any sections by Jet Spray method from downspout boot to outlet structure. |  | Due Diligence |  | 07 - Roofing |  |  |  |  | 0
[10 empty] | 0 | 0 | 0
Other
X | P | 16 | Grout and seal crack in concrete dumpster pad |  | Pick from Menu |  | 02 - Roads and Walks |  |  | 0 | 0 | 0
X | P | 17 | Trash enclosures are to be rebuilt with split-face CMU. Retain door frames and reface with composite pickets. Add man door/gate on left side of both. |  | Useful Life Duration Limit |  | 02 - Site Improvements |  |  | 0 | 0 | 0
X | P | 18 | Site sign to remain. | [6 empty] | 0 | 0 | 0
X | P | 19 | Benches to remain, at one bench, add wheelchair space |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 20 | Existing flag pole to remain. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 21 | Exterior metal railings to be repainted black. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 22 | Ensure grading at building perimeters provides positive drainage away from building foundations. |  | Architects Recommendation |  | Pick from Menu |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | BE | BUILDING EXTERIOR
X | N | 1 | R/R all gutters and downspouts. |  | Pick from Menu |  | 07 - Roofing |  |  | 0 | 0 | 0
X | N | 2 | R/R all thru-wall building exhaust louvers, dryer vents and vent caps. R/R all sealants. |  | Pick from Menu |  | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
X | P | 3 | R/R existing aluminum single-hung windows with new vinyl energy-efficient single-hung windows. |  | Useful Life Duration Limit |  | 08 - Windows |  |  | 0 | 0 | 0
X | N | 4 | R/R all sealants and caulking at all penetrations and control/expansion joints. |  | Due Diligence |  | 07 - Waterproofing |  |  | 0 | 0 | 0
X | P | 5 | R/R all exterior lighting to upgraded LED lighting package, provide Energy Star fixtures or lamps when available. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 6 | R/R all wall mounted security lighting. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 7 | Remove shutters and patch mounting holes with color matching material, no new shutters to be installed. |  | Architects Recommendation |  | 08 - Windows |  |  | 0 | 0 | 0
X | P | 8 | Paint decorative EIFS, stucco same color as original plans, eliminate green paint on surrounding round "medallions". |  | Due Diligence |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | P | 9 | Repaint townhouse "doors" as original plans |  | Due Diligence |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | AT | ATTIC
X | N | 1 | Upgrade building attic insulation to R49 minimum. Insulate all ductwork. |  | Pick from Menu |  | 07 - Insulation |  |  | 0 | 0 | 0
0
|  | CA | COMMON AREA (GENERAL ALL FLOORS)
X |  | 1 | See Corridors, Lobbies, Lounges and Common Area Finishes below. | [6 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
FIRST FLOOR
|  | EV | ENTRY VESTIBULE
X | P | 1 | R/R existing ceramic tile and base, install new walk-off carpet tile and vinyl cove base. |  | Design Element |  | 09 - Tile Work |  |  | 0 | 0 | 0
X | P | 2 | Install new access control system. |  | Pick from Menu |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 3 | Repaint walls and ceiling. |  | Design Element |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | P | 4 | R/R existing lighting and replace with new LED fixtures. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 5 | Storefront - R/R main entry doors and operators |  | Pick from Menu |  | 08 - Doors |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | FFL | FIRST FLOOR LOBBY
X | P | 1 | Existing floor tile to remain. |  | Design Element |  | 06 - Finish Carpentry |  |  | 0 | 0 | 0
X | P | 2 | Protect existing handrail. Sand and repair any damaged areas. |  | Architects Recommendation |  | 06 - Finish Carpentry |  |  | 0 | 0 | 0
X | P | 3 | New 2 tone paint, one color above handrail/chair rail and contrasting color below. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | P | 4 | R/R existing common area lighting with new LED fixture package. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 5 | R/R all interior signage with new National Church Residences standard signage package. |  | [Owner i.e. NCR] Design Standard | entire building | 10 - Specialities |  |  | 0 | 0 | 0
X | N | 6 | R/R window sills with cultured marble sills. |  | [Owner i.e. NCR] Design Standard |  | 08 - Windows |  |  | 0 | 0 | 0
X | N | 7 | R/R window treatments. |  | [Owner i.e. NCR] Design Standard |  | 12 - Blinds and Shades, Artwork |  |  | 0 | 0 | 0
X | P | 8 | R/R existing electric water cooler with new ADA electric water cooler with bottle filler. |  | Code Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | MTR | FIRST FLOOR MECHANICAL/ELECTRICAL
X | P | 1 | Clean and repair existing ductwork and supply grille for make up air unit. |  | Due Diligence |  | 15 - Heat and Ventilation |  |  |  | 0 | 0
X | P | 2 | R/R existing lighting with new LED fixture package. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | TR | FIRST FLOOR TRASH ROOM
X |  |  | See Trash Room below |  |  | picked up below |  |  |  | 0 | 0 | picked up below
|  | EEQ | FIRST FLOOR ELEVATOR EQUIPMENT ROOM
X | M | 1 | Work to be completed per elevator report once provided (full modernization). See Elevator below |  | [Owner i.e. NCR] Design Standard | picked up below | 14 - Elevators |  |  | 0 | 0 | 0
X | M | 2 | Install concrete joint sealant at cracks in floor and reseal concrete. |  | Due Diligence |  | 03 - Concrete |  |  | 0 | 0 | 0
X | M | 3 | R/R existing lighting with new LED fixture package. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | RR | FIRST FLOOR COMMON AREA RESTROOMS
X | N | 1 | R/R existing plumbing fixtures. |  | Due Diligence |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | N | 2 | Install new low flow 17” to 19” ADA compliant toilet 18” from side wall. |  | Code Requirement | included in cost above | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | N | 3 | Install new ADA compliant lavatory and faucet (per drawings) 15" from side wall. Provide scald and abrasion protection on piping below counter. |  | Code Requirement | included in cost above | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | N | 4 | R/R existing grab bars and install per ANSI requirements. |  | Code Requirement |  | 10 - Specialities |  |  | 0 | 0 | 0
X | N | 5 | Install new toilet accessories in code compliant locations (tissue dispenser, towel dispenser, mirror, sanitary napkin disposal in Women's). |  | Code Requirement |  | 10 - Specialities |  |  | 0 | 0 | 0
X | N | 6 | R/R existing exhaust fan. |  | Useful Life Duration Limit |  | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
X | N | 7 | New wall tile wainscot at 5'-0" a.f.f. on wet walls of restrooms. |  | [Owner i.e. NCR] Design Standard |  | 09 - Tile Work |  |  | 0 | 0 | 0
X | P | 8 | Paint walls above tile and ceilings. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | P | 9 | R/R lighting and upgrade with LED fixtures. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | N | 10 | R/R existing flooring with new ceramic tile flooring and ceramic tile base. |  | [Owner i.e. NCR] Design Standard |  | 09 - Tile Work |  |  | 0 | 0 | 0
| P | 11 | Door hardware to include occupancy indicator. |  | Code Requirement |  | 08 - Doors |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | MO | FIRST FLOOR MANAGEMENT OFFICES
Property Manager Office
X | N | 1 | R/R all existing flooring and base. Install new LVP flooring and wood base. |  | [Funding Agency i.e. HUD] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 2 | R/R lighting and upgrade with LED fixtures. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 3 | Paint walls and ceiling. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | P | 4 | Relocate rent drop box to property manager's office. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 5 | HVAC controls in the room need individual controls. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | N | 6 | R/R window sills with cultured marble sills. |  | [Owner i.e. NCR] Design Standard |  | 08 - Windows |  |  | 0 | 0 | 0
X | N | 7 | R/R window treatments. |  | [Owner i.e. NCR] Design Standard |  | 12 - Blinds and Shades, Artwork |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Control Room
X | N | 8 | R/R all existing flooring and base. Install new LVP flooring and wood base. |  | Pick from Menu |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 9 | Add mailbox system for internal mail to resident in control room 04. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 10 | Relocate rent drop box to property manager's office. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 11 | HVAC controls in the room need individual controls. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 12 | R/R lighting and upgrade with LED fixtures. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 13 | Paint walls and ceiling. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | N | 14 | R/R window sills with cultured marble sills. |  | [Owner i.e. NCR] Design Standard |  | 08 - Windows |  |  | 0 | 0 | 0
X | N | 15 | R/R window treatments. |  | [Owner i.e. NCR] Design Standard |  | 12 - Blinds and Shades, Artwork |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | MP | FIRST FLOOR MULTI-PURPOSE ROOM/COMMUNITY ROOM
X | N | 1 | R/R all existing flooring and base. Install new LVP flooring and wood base. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 2 | Add new standard NCR fireplace and bookshelf wall. |  | [Owner i.e. NCR] Design Standard |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 3 | Add a new serving island per plans. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 4 | Add new doors with side light between lobby and community room. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 5 | R/R lighting and upgrade with LED fixtures. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 6 | Paint walls and ceiling. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | N | 7 | R/R window sills with cultured marble sills. |  | [Owner i.e. NCR] Design Standard |  | 08 - Windows |  |  | 0 | 0 | 0
X | N | 8 | R/R window treatments. |  | [Owner i.e. NCR] Design Standard |  | 12 - Blinds and Shades, Artwork |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | MPK | FIRST FLOOR MULTI-PURPOSE ROOM KITCHEN/COMMUNITY ROOM KITCHEN
X | N | 1 | R/R existing flooring and base with new LVT flooring and wood base. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | N | 2 | All flooring is to extend under all removeable equipment/appliances and under cabinets. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 3 | R/R lighting and upgrade with LED fixtures. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 4 | R/R existing kitchen cabinets with new cabinets and wire pulls. Base cabinets to be 32” ADA accessible with roll out shelving. |  | [Owner i.e. NCR] Design Standard |  | 11 - Cabinets |  |  | 0 | 0 | 0
X | P | 5 | Install new quartz countertops. |  | [Owner i.e. NCR] Design Standard | included in line above | 10 - Specialities |  |  | 0 | 0 | 0
X | P | 6 | Install ADA compliant double bowl sink with lever faucet, insulate piping, provide valence and clear open space below. |  | [Owner i.e. NCR] Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | N | 7 | Install Insinkerator Badger 5 disposal. |  | [Owner i.e. NCR] Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 8 | New appliances include refrigerator, dishwasher, wall oven combo with microwave and built in wall kit. |  | [Owner i.e. NCR] Design Standard |  | 11 - Special Equipment |  |  | 0 | 0 | 0
X | P | 9 | Install under counter mount task lighting. |  | [Owner i.e. NCR] Design Standard |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 10 | Kitchen pass-through window to be removed. |  | [Owner i.e. NCR] Design Standard |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 11 | Paint walls and ceiling. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | JC | FIRST FLOOR JANITOR CLOSET
X |  |  | See Janitor Closets
|  | ST | FIRST FLOOR STAIRWELLS
X |  |  | See Stairwells
SECOND FLOOR
|  | SFL | SECOND FLOOR SUPPORT
X | P | 1 | R/R existing flooring and base. Install new flooring (TBD). |  | Pick from Menu |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
x | P | 2 | R/R lighting and upgrade with LED fixtures. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 3 | Paint walls and ceiling. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | P | 6 | Add new walls and doors per plan to enclose room 64. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 5 | Demo rooms 64, 65, 67, 68, 69, 70, 71 & 72. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | P | 6 | Decommission restrooms 73a & 73b. Rooms to become storage. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | JC | SECOND FLOOR JANITOR CLOSET & MECHANICAL ROOMS
X |  |  | See Janitor Closets | [8 empty] | picked up below
|  | TR | SECOND FLOOR TRASH ROOM
X |  |  | See Trash Room | [8 empty] | picked up below
|  | LR | SECOND FLOOR LAUNDRY ROOM
X |  |  | See Laundry Rooms | [8 empty] | picked up below
|  | CEL | SECOND FLOOR CORRIDORS, ELEVATOR LOBBY
X |  |  | See Corridor, Elevator Lobby | [8 empty] | picked up below
|  | S2 | SECOND FLOOR STAIRWELLS
|  |  | See Stairwells | [8 empty] | picked up below
THIRD FLOOR
|  | JC | THIRD FLOOR JANITOR CLOSET
X |  |  | See Janitor Closets | [8 empty] | picked up below
|  | TR | THIRD FLOOR TRASH ROOM
X |  |  | See Trash Room | [8 empty] | picked up below
|  | LR | THIRD FLOOR LAUNDRY ROOM
X |  |  | See Laundry Rooms | [8 empty] | picked up below
|  | CEL | THIRD FLOOR CORRIDORS, ELEVATOR LOBBY
X |  |  | See Corridor, Elevator Lobby | [8 empty] | picked up below
|  | S3 | THIRD FLOOR STAIRWELLS
X |  |  | See Stairwells | [8 empty] | picked up below
FOURTH FLOOR
|  | JC | FOURTH FLOOR JANITOR CLOSET
X |  |  | See Janitor Closets | [8 empty] | picked up below
|  | TR | FOURTH FLOOR TRASH ROOM
X |  |  | See Trash Room | [8 empty] | picked up below
|  | LR | FOURTH FLOOR LAUNDRY ROOM
X |  |  | See Laundry Rooms | [8 empty] | picked up below
|  | CEL | FOURTH FLOOR CORRIDORS, ELEVATOR LOBBY
X |  |  | See Corridor, Elevator Lobby | [8 empty] | picked up below
|  | S3 | FOURTH FLOOR STAIRWELLS
X |  |  | See Stairwells | [8 empty] | picked up below
COMMON ROOMS
|  | JC | JANITOR CLOSETS (3) FIRST, SECOND AND THIRD FLOORS (ALSO SMALL MECHANICAL ROOMS)
X | N | 1 | R/R existing VCT flooring and base with new VCT and vinyl base. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | N | 2 | R/R mop sink, faucet and surround. |  | Green Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 3 | R/R lighting and upgrade with LED fixtures. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 4 | Paint walls and ceiling per finish schedule. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | TR | TRASH ROOMS (ALL FLOORS)
X | P | 1 | Paint walls and ceiling per finish schedule. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | N | 2 | R/R existing flooring with LVP flooring throughout per finish schedule. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | N | 3 | R/R trash door handle with new accessible handle. |  | Code Requirement |  | 08 - Doors |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | LR | LAUNDRY ROOMS (2) (FIRST & THIRD FLOORS)
X | P | 1 | R/R lighting and upgrade with LED fixtures. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | N | 2 | R/R all existing flooring and base. Install new LVP flooring and wood base. |  | Pick from Menu |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 3 | Paint walls and ceiling per finish schedule. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | P | 4 | Room 86 will become a new laundry room. Provide new washers, dryers, and quartz countertops. |  | Pick from Menu |  | Pick from Menu |  |  | 0 | 0 | 0
X | N | 5 | R/R plam work counter. Mount at 34" a.f.f. Install ADA compliant laundry sink with ADA compliant meanuverablity spaces, lever faucet. Insulate piping, provide valence and clear open space below. |  | [Owner i.e. NCR] Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | N | 6 | R/R window sills with cultured marble sills. |  | [Owner i.e. NCR] Design Standard |  | 08 - Windows |  |  | 0 | 0 | 0
X | N | 7 | R/R window treatments. |  | [Owner i.e. NCR] Design Standard |  | 12 - Blinds and Shades, Artwork |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | S | STAIRWELLS (2) (FIRST, SECOND, THIRD, FOURTH FLOORS)
X | N | 1 | R/R existing stair doors and frames per door schedule. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | N | 2 | R/R existing stair treads with new vinyl stair treads. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | N | 3 | R/R all flooring and base. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 4 | Paint entire stairwell (walls & ceiling). |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | P | 5 | R/R existing light fixtures with new LED fixtures. |  | [Owner i.e. NCR] Design Standard |  | 16 - Electrical |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | CEL | CORRIDORS, ELEVATOR LOBBY
X | P | 1 | Protect existing handrail. Sand and repair any damaged areas. Refinish per finish schedule. |  | Architects Recommendation | Verify if existing base is to remain or be replaced. | 06 - Finish Carpentry |  |  | 0 | 0 | 0
X | N | 2 | Provide new wood chair rail on side opposite handrail. |  | [Owner i.e. NCR] Design Standard |  | 06 - Finish Carpentry |  |  | 0 | 0 | 0
X | P | 3 | New 2-tone paint, one color above handrail/chair rail and contrasting color below. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | P | 4 | R/R existing common area lighting with new LED fixture package. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 5 | R/R all interior signage with new National Church Residences standard signage package. |  | [Owner i.e. NCR] Design Standard | included in First Floor Lobby above | 10 - Specialities |  |  | 0 | 0 | 0
X | P | 6 | Install cover plates over all existing junction boxes where equipment was removed. Paint to match wall color. |  | Architects Recommendation |  | 16 - Electrical |  |  | 0 | 0 | 0
X | N | 7 | R/R window sills with cultured marble sills. |  | [Owner i.e. NCR] Design Standard |  | 08 - Windows |  |  | 0 | 0 | 0
X | N | 8 | R/R window treatments. |  | [Owner i.e. NCR] Design Standard |  | 12 - Blinds and Shades, Artwork |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | CAF | COMMON AREA FINISHES
X | N | 1 | Use Green Label carpeting and tile. Use Low/No VOC Paints, Primers, Adhesives and Sealants. |  | Green Requirement |  | 01 - General Requirements |  |  | 0 | 0 | 0
X | P | 2 | R/R existing ceiling grid and tile with new per finish schedule. |  | [Owner i.e. NCR] Design Standard |  | 09 - Acoustical |  |  | 0 | 0 | 0
X | N | 3 | R/R existing flooring with new carpet or LVP flooring throughout per finish schedule. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 4 | Sand and repair any damaged areas on existing handrails and base. Refinish per finish schedule. |  | Architects Recommendation |  | 06 - Finish Carpentry |  |  | 0 | 0 | 0
X | N | 5 | Provide new wood chair rail on side opposite handrail. |  | Architects Recommendation |  | 06 - Finish Carpentry |  |  | 0 | 0 | 0
X | N | 6 | R/R window sills with new cultured marble window sills. |  | [Owner i.e. NCR] Design Standard |  | 08 - Windows |  |  | 0 | 0 | 0
X | N | 7 | R/R all window treatments. |  | [Owner i.e. NCR] Design Standard |  | 12 - Blinds and Shades, Artwork |  |  | 0 | 0 | 0
X | N | 8 | Install new door casings at all new door frames and existing door frames to remain per finish schedule. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | P | 9 | Repaint 100% of all common areas and administrative areas. |  | Architects Recommendation |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | N | 10 | R/R existing public toilet flooring with new ceramic tile flooring and ceramic tile base. |  | [Owner i.e. NCR] Design Standard |  | 09 - Tile Work |  |  | 0 | 0 | 0
X | N | 11 | R/R existing closet shelving with new vinyl coated wire shelving. Provide shelf at accessible reach height |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | DR | COMMON AREA DOORS AND FRAMES
X | N | 1 | R/R all common area interior doors and frames with new solid core MDF 2-panel doors (pre-finished) and frames per door schedule. Doors to be Masonite Safe Sound or equal. Install new stained wood trim per finish schedule. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | P | 2 | Refer to the door schedule for new doors. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | N | 3 | R/R all interior stair doors and frames with new insulated hollow metal 2-panel doors (pre-primed) and frames per door schedule. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | N | 4 | R/R all unit entry doors and frames with new solid core MDF 6-panel doors (pre-finished) and frames per door schedule. Doors to be Masonite Safe Sound or equal. Install new stained wood trim per finish schedule. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | N | 5 | HC Units – new unit interior doors and frames as shown on plans. Doors to be Masonite Safe Sound or equal. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | N | 6 | Standard Units – new unit interior doors and frames as shown on plans. Doors to be Masonite Safe Sound or equal. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | DH | COMMON AREA AND UNIT DOOR HARDWARE
X | N | 1 | R/R all door hardware through out with new hardware package at both new and existing doors to remain. Install new door closers at all unit entry doors, public restrooms, fire doors, laundry, mechanical room, electric rooms, and exterior doors. Hardware shall be from single source mfr. and finish and to be based on Schlage ‘AL’ series with Jupiter lever handle design. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | P | 2 | Refer to the door schedule for new doors. Hardware shall be from single source mfr. and finish and to be based on Schlage ‘AL’ series with Jupiter lever handle design. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | N | 3 | R/R all unit entry door hardware with deadbolt lock and passage lever handset. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | N | 4 | Install new unit door combination knocker/peep hole with 2nd lower peep hole at HC units only. |  | Code Requirement |  | 08 - Doors |  |  | 0 | 0 | 0
X | N | 5 | At all unit interior doors, provide cost to install third hinge at existing frames. |  | [Owner i.e. NCR] Design Standard | Verify if existing frames are to remain | 08 - Doors |  |  | 0 | 0 | 0
X | N | 6 | At public restrooms door hardware shall indicate “occupied” or “vacant.” |  | Code Requirement | In costs for public RR | 08 - Doors |  |  | 0 | 0
X | N | 7 | Install “prop-open” alarms at exterior exit doors from stairs and door adjacent Service Coord.). |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
LIVING UNITS OVERVIEW
X |  | • One hundred (100) total units with eighty-eight (88) efficiency standard rental units, ten (10) efficiency units designated for Handicap accessibility, two (2) efficiency units designated for sight and visual impairments. • The three (10) handicap accessible units will be restructured to provide code required access to the greatest extent possible (5%). • Two (2) existing dwelling units will be designated as a unit for sensory impairment (2%).
|  | U | ALL UNITS
Total (#) of units: 100
General
X | P | 1 | Install new flooring to limits shown on drawings. Use Green Label tile. Use Low/No VOC Paints, Primers, Adhesives and Sealants. |  | Green Requirement |  | 01 - General Requirements |  |  | 0 | 0
X | M | 2 | 20 s.f. per unit allowance for floor prep. |  | Due Diligence |  | 01 - General Requirements |  |  | 0 | 0 | 0
X | M | 3 | Include provisions to repair all damaged existing drywall within living units – 10 sf allowance per unit, provide a unit cost for damage over 10 sf per unit. |  | Due Diligence |  | 09 - Drywall |  |  | 0 | 0 | 0
X | P | 4 | R/R all existing unit lighting with new upgraded LED lighting package. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | N | 5 | Install wall mounted package shelves at corridor side of dwelling unit entry. |  | [Owner i.e. NCR] Design Standard | Does N^^ want these? | 10 - Specialities |  |  | 0 | 0
[10 empty] | 0 | 0 | 0
Entry Foyer
X | N | 6 | R/R existing flooring with new vinyl plank flooring and wood base with roman ogee. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Living Area
X | P | 7 | R/R existing flooring with new vinyl plank flooring and wood base with roman ogee. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
Bedroom
[10 empty] | 0 | 0 | 0
Kitchen/Dining
X | P | 8 | Install non-slip vinyl plank flooring extended under all removable equipment and removable cabinetry to walls. |  | [Owner i.e. NCR] Design Standard | see above | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 9 | Install 4” vinyl cove base. |  | [Owner i.e. NCR] Design Standard | see above | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 10 | Install quartz counter work space. |  | [Owner i.e. NCR] Design Standard | Only in accessible units | 10 - Specialities |  |  | 0 | 0 | 0
X | P | 11 | R/R existing sink and garbage disposal with new ADA compliant singleX bowl sink with lever faucet and garbage disposal. Insulate plumbing. Install aerator on kitchen faucet. |  | [Owner i.e. NCR] Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 12 | Replace all appliances with Client Standard black appliances. |  | [Owner i.e. NCR] Design Standard |  | 11 - Special Equipment |  |  | 0 | 0 | 0
X | P | 13 | Install frost free refrigerator. |  | [Owner i.e. NCR] Design Standard | see above | 11 - Special Equipment |  |  | 0 | 0 | 0
X | P | 14 | Provide full height grease shield at range. Panel to be stainless steel with matching screws. |  | [Owner i.e. NCR] Design Standard |  | 07 - Sheet Metal |  |  | 0 | 0 | 0
X | P | 15 | Install under cabinet mount task lighting. |  | [Owner i.e. NCR] Design Standard |  | 16 - Electrical |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Bathroom
X | P | 16 | R/R vanity sink and controls; install aerator on lavatory faucet. |  | [Owner i.e. NCR] Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 17 | Install low flow 17” to 19” ADA compliant toilet. |  | Code Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 18 | R/R exhaust fan/light. |  | Useful Life Duration Limit |  | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | UF | UNIT FINISHES - ALL
X | P | 1 | R/R window sills with cultured marble sills. |  | [Owner i.e. NCR] Design Standard | see above | 08 - Windows |  |  | 0 | 0 | 0
X | P | 2 | R/R window blinds with new horizontal window blinds. |  | [Owner i.e. NCR] Design Standard | see above | 12 - Blinds and Shades, Artwork |  |  | 0 | 0 | 0
X | P | 3 | R/R window treatments. |  | [Owner i.e. NCR] Design Standard |  | 12 - Blinds and Shades, Artwork |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | UDF | UNIT DOORS AND FRAMES
X | N | 1 | New doors and frames as shown on plans. Door frames to be factory primed. Doors located along accessible path to be 36" frames to maintain required 32" clear opening. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
X | N | 2 | R/R all doors, frames and trim within unit with 2-panel wood doors, wood frames and casing trim per finish schedule. Paint to match trim. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | UDH | UNIT DOOR HARDWARE
X | N | 1 | Replace all door hardware with Schlage ‘AL’ series with Jupiter lever handle design. |  | [Owner i.e. NCR] Design Standard |  | 08 - Doors |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
MEP ITEMS
X |  |  | MEP items can be found below within the dedicated MEP fields
|  | HCU | HC LIVING UNIT SPECIFIC
Total (#) of units: 10 HC & 2 SI = 12 TOTAL
X | P | 1 | Repaint 100% of unit. Use Low/No VOC Paints, Primers, Adhesives and Sealants. |  | Green Requirement |  | 01 - General Requirements |  |  | 0 | 0 | 0
X | P | 2 | Repair textured ceilings at new work. Texture to match existing. |  | [Owner i.e. NCR] Design Standard |  | 09 - Drywall |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Entry Foyer
X | N | 3 | R/R existing linen closet shelving with new adjustable vinyl coated wire shelving. Provide shelf at accessible reach height. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | N | 4 | Remove existing closet shelving and rod, reinstall after closet walls have been painted. Replace any damaged shelving with new adjustable wire shelving to match. Provide shelf at accessible reach height. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Living Area
X | P | 5 | R/R existing flooring with new vinyl plank flooring. Install new painted wood base with roman ogee. |  | [Housing Agency i.e. OHFA] Design Standard | standard for carpet in HC living rooms? | 09 - Resilient Flooring |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Bedroom
X | P | 6 | R/R existing flooring with new vinyl plank flooring. Install new painted wood base with roman ogee. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 7 | Remove existing closet shelving, reinstall after closet walls have been painted. Replace any damaged shelving with new wire shelving to match. Provide shelf at accessible reach height. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | P | 8 | Install new switched ceiling fan/light combo. |  | [Owner i.e. NCR] Design Standard |  | 16 - Electrical |  |  | 0 | 0 | 0
X | M | 9 | Relocate electrical panel. Height of top breaker to be at 48” max. |  | Code Requirement | Need to verify height of existing panels | 16 - Electrical |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Kitchen/Dining
X | P | 10 | Kitchen to meet current ANSI unit type ‘A’ requirements as permitted by existing physical conditions. Demo and reconfigure kitchen as shown on drawings. |  | Code Requirement |  | 06 - Rough Carpentry |  |  | 0 | 0 | 0
X | P | 11 | Reconfigure cabinets and countertop as shown on drawings. |  | Pick from Menu |  | 11 - Cabinets |  |  | 0 | 0 | 0
X | P | 12 | Install kitchen cabinets with wire pulls. Base cabinets to be 32” HC accessible with one roll out shelf. Roll-out shelf installed 15” min. a.f.f. |  | Pick from Menu | see above | 11 - Cabinets |  |  | 0 | 0 | 0
X | P | 13 | Install quartz countertops. |  | [Owner i.e. NCR] Design Standard |  | 10 - Specialities |  |  | 0 | 0 | 0
X | P | 14 | Install new client standard black appliances |  | [Owner i.e. NCR] Design Standard | see above | 11 - Special Equipment |  |  | 0 | 0 | 0
X | P | 15 | R/R recirculating range hood. Provide with fire canisters. Light and fan to be switched at backsplash. |  | [Owner i.e. NCR] Design Standard | $500/unit | 11 - Special Equipment |  |  | 0 | 0 | 0
X | N | 16 | R/R existing pantry shelving with new adjustable vinyl coated wire shelving. Provide shelf at accessible reach height. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Bathroom
X | P | 17 | Demo and reconfigure as shown on plan to accommodate 60" turning radius. |  | Code Requirement |  | 06 - Rough Carpentry |  |  | 0 | 0 | 0
X | P | 18 | Remove tub and surround. Install ½” beveled threshold 60” clear roll in type prefabricated fiberglass shower unit with ADA compliant grab bars, control valves and wand/slidebar locations at all HC units. |  | Code Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 19 | Install new grab bars and blocking at rear and side wall of toilet for 42” grab bar at side wall and 36” grab bar at rear wall. |  | Code Requirement |  | 11 - Appliances |  |  | 0 | 0 | 0
X | P | 20 | Install plastic laminate wall hung vanity with 30” min. clear open space centered on sink. Top of sink rim to be 34” max. 6" backsplash to be installed entire length of back wall. Insulate plumbing below sink. |  | Code Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 21 | R/R existing flooring and base with vinyl plank and vinyl cove base. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | M | 22 | Install new floor drain in HC unit bathroom. |  | [Housing Agency i.e. OHFA] Design Standard |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 23 | Provide solid blocking at rear and side wall of toilet for grab bar installation as shown on drawings. |  | Code Requirement |  | 06 - Rough Carpentry |  |  | 0 | 0 | 0
X | P | 24 | R/R all toilet accessories; toilet paper holder, mirror, medicine cabinet and towel bar. Install in HC compliant locations. |  | [Owner i.e. NCR] Design Standard |  | 10 - Specialities |  |  | 0 | 0 | 0
X | P | 25 | Remove existing closet shelving, reinstall after closet walls have been painted. Replace any damaged shelving with new wire shelving to match. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | SU | STANDARD LIVING UNITS - SPECIFIC
Total (#) of units: 88
X | P | 1 | Repaint 100% of unit. Use Low/No VOC Paints, Primers, Adhesives and Sealants. |  | Green Requirement |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Entry Foyer
X | N | 2 | R/R existing linen closet shelving with new adjustable vinyl coated wire shelving. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | N | 3 | R/R existing closet shelving and rod with new vinyl coated wire shelf and hanging rod. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Living Area
X | P | 4 | R/R existing flooring with new vinyl plank flooring. Install new painted wood base with roman ogee. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
Bedroom
X | P | 5 | R/R existing closet shelving and rod with new vinyl coated wire shelf and hanging rod. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
X | N | 6 | R/R existing flooring with new carpet flooring and wood base with roman ogee. |  | [Owner i.e. NCR] Design Standard |  | 09 - Resilient Flooring
[7 empty] | Pick from Menu |  |  | 0 | 0 | 0
Kitchen/Dining
X | P | 7 | Demo and reconfigure kitchen as shown on drawings. |  | Pick from Menu |  | 06 - Rough Carpentry |  |  | 0 | 0 | 0
X | P | 8 | Install kitchen cabinets with wire pulls. Base cabinets to be 33 1/2” HC accessible height. Wall cabinets to be set with top of bottom shelf at 46” a.f.f. |  | PCNA (2019) |  | 11 - Cabinets |  |  | 0 | 0 | 0
X | P | 9 | Install quartz countertops. |  | [Owner i.e. NCR] Design Standard |  | 10 - Specialities |  |  | 0 | 0 | 0
X | P | 10 | R/R recirculating range hood. Provide with fire canisters. |  | [Owner i.e. NCR] Design Standard | $300/unit | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
X | P | 11 | Install new client standard black appliances |  | [Owner i.e. NCR] Design Standard | see above | 11 - Special Equipment |  |  | 0 | 0
X | N | 12 | R/R existing pantry shelving with new adjustable vinyl coated wire shelving. |  | [Owner i.e. NCR] Design Standard |  | 09 - Painting and Decorating |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Bathroom
X | P | 13 | R/R existing flooring and base with new vinyl plank flooring and vinyl cove base. Extend flooring & base under vanity. |  | [Owner i.e. NCR] Design Standard | see above | 09 - Resilient Flooring |  |  | 0 | 0 | 0
X | P | 14 | R/R existing vanity and counter with new plastic laminate counter and removable vanity base. |  | Architects Recommendation |  | 06 - Finish Carpentry |  |  | 0 | 0 | 0
X | P | 15 | R/R shower head and controls with low flow fixture. Existing shower to remain. |  | Green Requirement |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 16 | R/R all toilet accessories; toilet paper holder, mirror, medicine cabinet and towel bar. |  | [Owner i.e. NCR] Design Standard |  | 10 - Specialities |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
MEP DISCIPLINES
|  | BS | BUILDING SECURITY/ACCESS CONTROL
X | P | 1 | All exterior building entrance doors shall be secured with Grade 1 locksets. The main entrance shall be equipped with new power assist switching aluminum entry system doors. Outer doors shall be accessible 24 hours a day, 7 days a week. Inner doors shall be secured with FOB access. Visitors can be admitted into the building remotely from the Manager’s Office or a resident unit. A visitor would notify either the office or living unit through the entrance telephone access system to gain admittance. Additionally, a visual display of the visitor will be provided to a display at the Manager’s Office and via television within individual Dwelling Units.. The door security system shall be programmable by the building manager via a personal computer. |  | [Owner i.e. NCR] Design Standard | see above | 08 - Doors |  |  | 0 | 0 | 0
X | M | 2 | R/R existing visitor intercom system with new Sentex ‘Ovation’ interfaced with Telephone system. Install at existing main entry vestibule. |  | Pick from Menu | included in EntryVestibule above | 16 - Electrical |  |  | 0 | 0 | 0
X | M | 3 | Provide keyless entry FOB system at building main entry interior vestibule door and exterior rear door to patio. |  | Pick from Menu |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 4 | R/R HC push pads and auto openers at exterior and interior main entry vestibule storefront doors. |  | Due Diligence | assumes wiring is good | 16 - Electrical |  |  | 0 | 0 | 0
X | M | 5 | Install “prop-open” alarm system at all exterior stairwell doors addressable to Manager’s Office. |  | [Owner i.e. NCR] Design Standard | included in Common Area Hardware above | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 6 | Security cameras are to be installed at all entrances of the building. |  | [Owner i.e. NCR] Design Standard |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 7 | Building Wi/Fi system to be installed. EC to provide power to equipment locations (coordinate with Low Voltage Contractor). |  | [Owner i.e. NCR] Design Standard |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | BS8 | Emergency call system is existing to remain. |  |  |  | 16 - Electrical |  |  |  |  | 0
[10 empty] | 0 | 0 | 0
|  | FP | FIRE/SMOKE PROTECTION
X | P | 1 | R/R all smoke detectors in all units. Each unit to include two detectors total - one in bedroom and one within the immediate vicinity of the bedroom. |  | Pick from Menu |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 2 | R/R smoke detectors in all common, administrative, maintenance, mechanical and storage areas. All smoke detectors shall be permanently connected to primary and secondary power supplies and installed per NFPA 72. |  | Pick from Menu |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 3 | R/R all carbon monoxide detectors in all units. |  | Code Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 4 | Reconfigure heads to provide full coverage in ADA dwelling units and all other new and modified spaces where wall and ceiling layouts are reconfigured. Provide new heads and escutcheon plates. |  | Due Diligence |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | FP5 | R/R fire alarm system with new addressable fire alarm system compliant with NFPA 72. |  | Due Diligence | Based on photos showing two different panels currently in building | 16 - Electrical
[10 empty] | 0 | 0 | 0
|  | P | PLUMBING
All Units
X | P | 1 | All faucets to have lever handle and temperature limiting device that conforms to ASSE 1070. |  | Code Requirement | ok | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 2 | Install new low flow ADA compliant toilets. Provide American Standard Cadet 3 Right Height Elongated Toilet (1.28GPF). |  | Green Requirement | ok | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 3 | Reconfigure plumbing for new fixture locations as shown on drawings. |  |  | see above | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 4 | R/R bathroom sinks and faucets. Faucets to have single lever handle and temperature limiting device that conforms to ASSE 1070. |  | Green Requirement | ok | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 5 | R/R kitchen sinks and faucets. Faucets to have lever handle and temperature limiting device that conforms to ASSE 1070. |  | Green Requirement | ok | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 6 | Standard units: R/R shower head with low flow fixture. |  | Green Requirement | included in Standard Unit costs above | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
HC Units
X | P | 7 | HC units: Provide 36” x 64” Clarion roll-in showers with pressure balancing valve conforming to ASSE 1016. |  | Code Requirement | included in HC Unit costs above | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 8 | Provide Truebro "Lavguard" plumbing insulation for handicap accessible sinks and lavatories. |  | Code Requirement | included in costs above | 10 - Specialities |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Building
X | P | 9 | All newly installed domestic water supply piping shall be copper. Provide alternate pricing for CPVC. |  | Pick from Menu |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | M | 10 | R/R two (2) gas fired boilers for hot water system |  | Pick from Menu |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | M | 11 | R/R two (2) booster pumps for hot water system |  | Pick from Menu |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | M | 12 | R/R one (1) 200 gallon storage tank for hot water system |  | Pick from Menu |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | M | 13 | R/R all domestic supply shut off valves. |  | Due Diligence |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | P | 14 | Fire stop all new and existing pipe penetrations at fire rated ceiling/wall penetrations. (allowance) |  | Code Requirement |  | 07 - Insulation |  |  | 0 | 0 | 0
X | P | 15 | Provide disposal for community room kitchen sink. |  | [Owner i.e. NCR] Design Standard | see above | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | M | 16 | Inspect all existing natural gas mains and supply lines. No deficiencies were identified in the PCNA report. |  | Due Diligence |  | 02 - Site Utilities |  |  | 0 | 0 | 0
X | M | 17 | Inspect all existing sanitary lines from building to street. Remove, repair, replace or clean as required. No deficiencies were identified in PCNA report. Provide allowance for any anticipated work. |  | Due Diligence |  | 02 - Site Utilities |  |  | 0 | 0 | 0
X | M | 18 | Provide 3” Watts 957OSY RPZ backflow preventer on domestic water line after meter. Provide drainage piping to nearest floor drain with air gap fitting. |  | Due Diligence |  | 02 - Site Utilities |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | M | HVAC
|  | 1 | R/R four pipe system |  | PCNA 2019 | [5 empty] | ???
All Units
X | M | 1 | R/R dwelling unit and common space thermostats. Provide large, digital screen, programmable thermostat, Johnson Controls #TEC3321. Mount thermostat at 47" AFF at top. Provide clear, lockable cover for thermostats in public spaces. |  | [Owner i.e. NCR] Design Standard |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 2 | Install new dwelling unit bathroom fan/light combination, controlled by motion sensor/timer. R/R exterior louver. |  | Useful Life Duration Limit | included in Unit costs above | 16 - Electrical |  |  | 0 | 0 | 0
X | N | 3 | Provide new kitchen exhaust fan. Re-use existing kitchen exhaust ductwork. |  | Useful Life Duration Limit | included in Unit costs above | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
HC Units
[10 empty] | 0 | 0 | 0
Building
X | M | 4 | R/R two (2) gas fired boilers for heating system along with pumps |  | Pick from Menu |  | 15 - Plumbing and Hot Water |  |  | 0 | 0 | 0
X | M | 5 | R/R existing fan coil units throughout |  | Pick from Menu |  | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
| P | 6 | R/R existing electric furnace for common areas |  | PCNA (2019) | Not found, all air equipment fan coils | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
X | M | 7 | R/R existing through wall PTAC units in common areas |  | Pick from Menu |  | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
X | P | 8 | Fire stop all new and existing pipe penetrations at fire rated ceiling/wall penetrations. |  | Code Requirement |  | 07 - Insulation |  |  | 0 | 0 | 0
X | N | 9 | R/R common area electric unit heaters. |  | Useful Life Duration Limit |  | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
X | M | 10 | Existing air devices are to remain. Remove, clean and re-install. If any existing air devices are damaged, notify the Architect. |  | Due Diligence |  | 15 - Air Conditioning |  |  | 0 | 0 | 0
X | M | 11 | R/R all mechanical wall vents/louvers. |  | Useful Life Duration Limit | included in Building Exterior above | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
X | M | 12 | Clean, seal and insulate all existing ductwork. |  | Due Diligence |  | 07 - Insulation |  |  | 0 | 0 | 0
X | M | 13 | R/R existing exhaust fan in Elevator Machine room. |  | Useful Life Duration Limit | will the elev machine room have any work? | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
X | M | 14 | R/R common area toilet rooms exhaust fan/light. New exhaust fan/light connected to existing ductwork. |  | Useful Life Duration Limit | included in Common Restroom above | 15 - Heat and Ventilation |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | E | ELECTRICAL
All Units
X | P | 1 | R/R all HC and Standard unit lighting with new Energy Star rated fixtures. |  | [Owner i.e. NCR] Design Standard | included in costs above | 16 - Electrical |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
HC Units
X | P | 2 | Install in HC dwelling units tamper resistant receptacles per NEC. Provide AFCI protection per NEC. |  | Code Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 3 | Provide GFCI protected receptacles per NEC in HC unit kitchens, common laundry and common kitchen |  | Code Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 4 | Install visual/audible alarm devices in HC unit and Sensory impaired unit living rooms, bedrooms and bathrooms. |  | Code Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | M | 5 | Install new ceiling fan/light combo in HC unit bedrooms centered in room. |  | [Owner i.e. NCR] Design Standard | may require relocation of junction box in ceiling included in costs above | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 6 | R/R all HC unit switches to be no higher than 48" a.f.f. to top of device. |  | Code Requirement | included in costs above | 16 - Electrical |  |  | 0 | 0 | 0
[7 empty] | Pick from Menu |  |  | 0 | 0 | 0
Building
X | N | 7 | Install Emergency Generator |  | Pick from Menu |  | 02 - Site Utilities |  |  | 0 | 0 | 0
X | P | 8 | R/R all building interior lighting with new upgraded LED lighting package, provide Energy Star fixtures or lamps when available. |  | Green Requirement | included in costs above | 16 - Electrical |  |  | 0 | 0 | 0
X | M | 9 | R/R existing common area exit signs and emergency lighting with new battery backup fixtures. Verify exit lighting is adequate and operable, otherwise provide new fixtures required by authority having jurisdiction. |  | Code Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | M | 10 | In rooms/spaces where wiring is being replaced, light switches, thermostats and other environmental controls are to be placed in accessible locations no higher than 48” a.f.f to top of device. and electrical receptacles, phone jacks and data ports are installed at 18” a.f.f. |  | Code Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | M | 11 | R/R all exterior building lighting (including sconces at patio & security lights) to upgraded LED lighting package, provide Energy Star fixtures or lamps when available. |  | Green Requirement |  | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 12 | R/R all common area switches to be no higher than 48" a.f.f. to top of device. |  | Code Requirement | included in costs above | 16 - Electrical |  |  | 0 | 0 | 0
X | M | 13 | See Building Security Access Control Section above. |  | [Owner i.e. NCR] Design Standard | included in costs above | 16 - Electrical |  |  | 0 | 0 | 0
X | M | 14 | Install “prop-open” alarms at new exterior corridor doors. |  | [Owner i.e. NCR] Design Standard | included in costs above | 16 - Electrical |  |  | 0 | 0 | 0
X | M | 15 | Remove existing corridor emergency call indicator lights. |  | [Owner i.e. NCR] Design Standard | included in costs above | 16 - Electrical |  |  | 0 | 0 | 0
X | P | 16 | R/R or install new magnetic door hold opens at all common area doors within fire rated assemblies connected to the building fire alarm system. |  | Code Requirement |  | 08 - Doors |  |  | 0 | 0 | 0
X |  | 17 | Telephone distribution existing to remain. |  |  |  | 16 - Electrical |  |  | 0 | 0 | 0
X |  | 18 | Cable distribution system existing to remain. |  |  |  | 01 - General Requirements |  |  | 0 | 0 | 0
[7 empty] | Pick from Menu |  |  | 0 | 0 | 0
|  | EV | ELEVATOR
X | P | 1 | Elevator modernization: equipment (including pump, power supply and controllers), ADA compliant controls and interior finish upgrade modernization to be included; provide stair lift for duration of time that the elevator will be out of service. See elevator specification for complete scope. Abatement: to be included in construction cost estimate. |  | Useful Life Duration Limit |  | 14 - Elevators |  |  | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Scope Questions / Clarifications:
[8 empty] | Number of Units |  |  | 100 | 100 | 100 | 100 | 100
[8 empty] | Construction Budget |  |  | 0 | 0 | 0 | 0 | 0
[8 empty] | Subtotal construction cost |  |  | 0 | 0 | 0 | 0 | 0
[8 empty] | 6% safe harbor general conditions |  |  | 0 | 0 | 0 | 0 | 0
[8 empty] | 2% safe harbor overhead |  |  | 0 | 0 | 0 | 0 | 0
[8 empty] | 6% safe harbor fee |  |  | 0 | 0 | 0 | 0 | 0
[8 empty] | P&P bond |  |  | 0 | 0 | 0 | 0 | 0
[8 empty] | Builders risk (assumed to be by Owner) |  |  | 0 | 0 | 0 | 0 | 0
[8 empty] | Total |  |  | 0 | 0 | 0 | 0 | 0
[8 empty] | Cost per unit Goal |  |  | 0 | 0
[8 empty] | Cost per unit |  |  | 0 | 0 | 0 | 0 | 0

## Trade Item
Pick from Menu | Sum from SCOPE
01 - General Requirements | 0
02 - Earth Work | 0
02 - Lawns and Plantings | 0
02 - Roads and Walks | 0
02 - Site Improvements | 0
02 - Site Utilities | 0
02 - Unusual Site Condition | 0
03 - Concrete | 0
04 - Masonry | 0
05 - Metals | 0
06 - Finish Carpentry | 0
06 - Rough Carpentry | 0
07 - Insulation | 0
07 - Roofing | 0
07 - Sheet Metal | 0
07 - Waterproofing | 0
08 - Doors | 0
08 - Glass | 0
08 - Windows | 0
09 - Acoustical | 0
09 - Drywall | 0
09 - Lath and Plaster | 0
09 - Painting and Decorating | 0
09 - Resilient Flooring | 0
09 - Tile Work | 0
09 - Wood Flooring | 0
10 - Specialities | 0
11 - Appliances | 0
11 - Cabinets | 0
11 - Special Equipment | 0
12 - Blinds and Shades, Artwork | 0
12 - Carpets | 0
13 - Special Construction | 0
14 - Elevators | 0
15 - Air Conditioning | 0
15 - Heat and Ventilation | 0
15 - Plumbing and Hot Water | 0
16 - Electrical | 0
SUBTOTAL (Structures) | 0
(Accessorty Structures)
TOTAL | 0

## Origin of Scope
Pick from Menu | Pick from Menu - Suggestions for Column A |  | Note: If the menu items don't show up in the drop down list on the SCOPE sheet you must edit the Data Validation in the Data tab
Code Requirement | Bldg Code - Requirement | 1st Priority - Meet code expectations
Accessibility Requirement | Elec Code - Requirement
Green Requirement | Mech Code - Requirement
Useful Life Duration Limit | Plumb Code - Requirement
[Housing Agency i.e. OHFA] Design Standard | Accessibilty Code - Req'mt
[Funding Agency i.e. HUD] Design Standard
[Owner i.e. NCR] Design Standard | [Housing Agency i.e. OHFA] - Green Requirement | 2nd Priority - Satisfying State Regulation Organizations
PCNA (2024) | [Housing Agency i.e. OHFA] - Accessibilty Req'mt
Due Diligence | [Housing Agency i.e. OHFA] - Design Requirement
Design Element
Architects Recommendation | [Funding Agency i.e. HUD] - Design Standard | 3rd Priority - Funding Partner Expectations
Phase 1 Report
Needs Questionnaire 2024 | Environmental Standards [i.e. LEED] | 4th Priority - Environmental Expectations
| [Owner i.e. NCR] Design Standard | 5th Priority - Owner Expectations
| Useful Life Duration Limit | 5th Priority - Items that don't fall under previous items. Would be first to be VE'd out of project
Due Diligence
Design Element
Architects Recommendation
| PCNA [Year] | Misc. source items that use the other sources for creating that document

## File Info
Creator | This chart was modified/created by Tony Killian. If you are having issues, he would be the first to ask concerning a resolution.
Locked Cell Password | bpiP8ssP8ss
ITEM
Abbreviations i.e. S1 | Can be updated by going to Home > Number > Number Format > Custom
Trade Items | Are not to be edited
Origin of Scope | Edit depending on client and resource documents
SCOPE | DO NOT DUPLICATE ROOMS IF THEY OCCUR ON MULTIPLE FLOORS, instead, instruct the floor category on each floor to a common room after the individual floors
Add and subtract rooms as needed for the project